## TARIFF WISE
PENDING RIPE INDUSTRIAL CONNECTIONS DETAIL ENDING 02-2021 IN RESPECT OF MEPCO
SR. NO | NAME OF DIVISION | Application |  | TARIFF | LOAD (KW) | DN ISSUANCE DATE | DN PAID ON | REASONS FOR PENDANCY | LAST DATE OF MONTH | NO. OF DAYS SINCE PAYMENT
|  | No. | Date
A | B | C | D | E | F | G | H | I | J | K
1 | Kabirwala | 345 | 2020-08-04 | B-1 | 20 | 2020-08-07 | 2020-08-13 | Civil Suit (right of way problem) | 2021-02-28 | 199
2 | M/Channu | 1042/B-1 | 13.07.20 | B-1 | 23 | 14.07.20 | 18.08.20 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 192
3 | M/Channu | 1048/B-1 | 26.08.20 | B-1 | 15 | 28.08.20 | 02.09.20 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 180
4 | Musa Pak | 12187 | 2020-08-31 | B-1 | 24 | 2020-09-02 | 2020-09-04 | Right of Way / Neighbor Hindrance | 2021-02-28 | 177
5 | M/Channu | 1047/B-1 | 21.08.20 | B-1 | 15 | 24.08.20 | 14.09.20 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 165
6 | APEast | 2515 | 26.08.20 | B-1 | 19.00 | 03.09.20 | 2020-10-02 | Court Case | 2021-02-28 | 149
7 | Kabirwala | 2515 | 2020-10-02 | B-1 | 24 | 2020-10-02 | 2020-10-09 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 142
8 | M/Channu | 1052/B-1 | 2020-09-15 | B-1 | 19 | 2020-09-25 | 2020-10-16 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 135
9 | Sahiwal-1 | 1197/B1 | 2020-10-12 | B-1 | 25 | 2020-10-19 | 2020-11-02 | Material not allocated | 28.02.21 | 118
10 | Sahiwal-1 | 1199/B1 | 2020-10-20 | B-1 | 25 | 2020-10-28 | 2020-11-02 | Material not allocated | 28.02.21 | 118
11 | SWL-II | 175/B-I | 2020-10-05 | B-1 | 18.85 | 2020-10-09 | 2020-11-06 | Particially material allocated | 28.02.21 | 115
12 | SWL-II | 177/B-I | 2020-10-19 | B-1 | 18.85 | 2020-10-22 | 2020-11-16 | Particially material allocated | 28.02.21 | 105
13 | SWL-II | 6194 | 2020-11-11 | B-1 | 18.85 | 2020-11-13 | 2020-11-16 | Particially material allocated | 28.02.21 | 105
14 | Kabirwala | 002484 | 2020-09-30 | B-1 | 19 | 2020-10-01 | 2020-11-16 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 104
15 | S.R.Alam | 15191011481/545 | 28.10.20 | B-1 | 15 | 2020-11-10 | 2020-11-19 | Material Allocated Work in Progress | 2021-02-28 | 101
16 | M/Channu | 1057/B-1 | 26.10.20 | B-1 | 19 | 03.11.20 | 19.11.20 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 101
17 | SWL-II | 178/B-I | 2020-10-23 | B-1 | 18.85 | 2020-10-29 | 2020-11-24 | Particially material allocated | 28.02.21 | 97
18 | Chishtian | 15831006960 | 25.10.20 | B-1 | 24 | 2020-11-18 | 2020-11-25 | Material recently allocated, work under progress | 28.02.21 | 95
19 | Hasilpur | 15451005691 | 24.11.20 | B-1 | 19 | 27.11.20 | 30-11-20 | During erection of poles, Hurdle created by street residents, Due to that Consumer provided an affidavit that he will provide the fard-e-malikiate of new site, til then his connection pending and will be installed at new site. | 2021-02-28 | 90
20 | Arifwala | 736/B-1 | 18.11.20 | B-1 | 18.65 | 23.11.20 | 30.11.20 | Material Allocated SR Prepared | 28.02.21 | 90
21 | Liaqatpur | 15632004650 | 12.11.2020 | B-1 | 19 | - | 01.12.2020 | 25 kVA T/Former | 28.02.2021 | 90
22 | Liaqatpur | 15633006951 | 05.11.2020 | B-1 | 19 | - | 30.11.2020 | 25 kVA T/Former, 02 No. 36' HT PCC & 02 No. 40' HT PCC Poles | 28.02.2021 | 90
23 | Sadiqabad | 15642007831 | 09.11.2020 | B-1 | 19 | - | 30.11.2020 | 25 kVA T/Former & 01 No. HT PCC Pole | 28.02.2021 | 90
24 | TAUNSA | 15265007607 | dt. 2.11.20 | B-1 | 18 | 22.11.20 | 23.11.20 | -do- | 28.02.21 | 90
25 | Sadiqabad | 15645000511 | 08.10.2020 | B-1 | 19 | - | 09.11.2020 | 25 kVA T/Former & 01 No. LT PCC Pole | 28.02.2021 | 90
26 | Khanewal | 15911003429 | 2020-11-02 | B-1 | 16 | 2020-11-24 | 2020-11-30 | Civil Suit (right of way problem) | 2021-02-28 | 90
27 | M/Channu | 1024/B-1 | 25.11.19 | B-1 | 15 | 28.11.19 | 03.12.19 | (Civil Suit) Right of way problem Now Revised Demand Notice Issued to Consumer vide Xen M/Channu DN No. 72716 dated 08.02.2021 DN PAID ON 10.02.21 | 2021-02-28 | 90
28 | S.R.Alam | 15191011118/532 | 2020-09-28 | B-1 | 24 | 2020-10-02 | 2020-12-08 | Material Allocated Work in Progress | 2021-02-28 | 82
29 | Arifwala | 729/B-1 | 26.10.20 | B-1 | 14.92 | 26.10.20 | 10.11.20 | Material Allocated SR Prepared | 28.02.21 | 80
30 | Arifwala | 742/B-1 | 03.12.20 | B-1 | 18.65 | 04.12.20 | 10.12.20 | Material Allocated SR Prepared | 28.02.21 | 80
31 | SWL-II | 7264 | 2020-12-02 | B-1 | 20 | 2020-12-07 | 2020-12-11 | Particially material allocated | 28.02.21 | 80
32 | M/Channu | 1059/B-1 | 19.11.20 | B-1 | 22 | 07.12.20 | 11.12.20 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 80
33 | Sadiqabad | 15645000533 | 26.10.2020 | B-1 | 19 | - | 11.12.2020 | 25 kVA T/Former & 01 No. HT PCC Pole | 28.02.2021 | 79
34 | Khanewal | 15912002539 | 2020-10-13 | B-1 | 16 | 2020-11-25 | 2020-12-14 | Material not drawn due to ERP prblem | 2021-02-28 | 76
35 | Kabirwala | 001873 | 2020-11-19 | B-1 | 17 | 2020-11-19 | 2020-12-14 | Material not drawn | 2021-02-28 | 76
36 | Arifwala | 737/B-1 | 23.11.20 | B-1 | 18.65 | 26.11.20 | 15.12.20 | Material Allocated SR Prepared | 28.02.21 | 75
37 | R.Y.Khan | 15618005997 | 29.11.2020 | B-1 | 19 | - | 15.12.2020 | 25 kVA T/Former & 02 No. HT PCC Poles | 28.02.2021 | 75
38 | CCW | 631/B-1 b | 07-12-20 | B-1 | 17 | 15-12-20 | 17-12-20 | Pole not installed by contractor | 28.02.21 | 73
39 | M/Channu | 1062/B-1 | 08.12.20 | B-1 | 16 | 08.12.20 | 21.12.20 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 70
40 | S.R.Alam | 15192010376/554 | 2020-12-04 | B-1 | 24 | 2020-12-17 | 2020-12-23 | Pole & rabbit Conductor not issued by Store | 2021-02-28 | 67
41 | Pakpattan | 951/BI | 02.11.20 | B-1 | 18.95 |  | 25.11.20 | Material allocated vide No.5087 dt 04.02.2021 work under process | 28.02.21 | 67
42 | Kot Addu | 15722011462 | 04.11.2020 | B-1 | 19 |  | 23.12.2020 | 20-Mtrs. 4/C PVC required | 28.02.2021 | 67
43 | Kabirwala | 003015 | 2020-12-08 | B-1 | 16 | 2020-12-11 | 2020-12-23 | Material not drawn | 2021-02-28 | 67
44 | Kabirwala | 003254 | 2020-12-22 | B-1 | 24 | 2020-12-22 | 2020-12-23 | Material not drawn | 2021-02-28 | 67
45 | Sahiwal-1 | 1201/B-1 | 2020-11-17 | B-1 | 25 | 2020-11-26 | 2020-12-24 | Material not allocated | 28.02.21 | 66
46 | Pakpattan | 949/BI | 23.10.20 | B-1 | 18.92 |  | 27.11.20 | Material allocated vide No.5087 dt 04.02.2021 work under process | 28.02.21 | 65
47 | Arifwala | 733/B-1 | 17.11.20 | B-1 | 18.65 | 19.11.20 | 26.11.20 | Material Allocated SR Prepared | 28.02.21 | 64
48 | SWL-II | 7363 | 2020-12-02 | B-1 | 20 | 2020-12-07 | 2020-12-28 | Particially material allocated | 28.02.21 | 63
49 | Khanewal | 15916002970 | 2020-12-03 | B-1 | 16 | 2020-12-22 | 2020-12-28 | Work under Progress | 2021-02-28 | 62
50 | Kabirwala | 001900 | 2020-11-27 | B-1 | 16 | 2020-11-28 | 2020-12-28 | Material not drawn | 2021-02-28 | 62
51 | TAUNSA | 15262007562 | dt. 12.11.20 | B-1 | 18 | 02.12.20 | 28.12.20 | Material allocated. Installation work is under process | 28.02.21 | 61
52 | Kabirwala | 003292 | 2020-12-28 | B-1 | 17 | 2020-12-28 | 2020-12-29 | Material not drawn | 2021-02-28 | 61
53 | S.R.Alam | 15191011874/556 | 2020-12-10 | B-1 | 24 | 2020-12-22 | 2020-12-30 | Pole & rabbit Conductor not issued by Store | 2021-02-28 | 60
54 | Arifwala | 743/B-1 | 03.12.20 | B-1 | 18.65 | 07.12.20 | 29.12.20 | Material Allocated SR Prepared | 28.02.21 | 60
55 | Khanewal | 15913003315 | 2020-11-18 | B-1 | 22 | 2020-12-21 | 2020-12-30 | Work under Progress | 2021-02-28 | 60
56 | Khanewal | 15913003830 | 2020-12-24 | B-1 | 16 | 2020-12-29 | 2020-12-30 | Work under Progress | 2021-02-28 | 60
57 | Kabirwala | 001919 | 2020-12-04 | B-1 | 23 | 2020-12-07 | 2020-12-30 | Material not drawn | 2021-02-28 | 60
58 | Kabirwala | 003148 | 2020-12-24 | B-1 | 16 | 2020-12-28 | 2020-12-30 | Material not drawn | 2021-02-28 | 60
59 | M/Channu | 1060/B-1 | 07.12.20 | B-1 | 23 | 17.12.20 | 30.12.20 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 60
60 | R.Y.Khan | 15618006135 | 18.12.2020 | B-1 | 19 | - | 31.12.2020 | 25 kVA T/Former & 03 No. HT PCC Poles | 28.02.2021 | 59
61 | Kabirwala | 003272 | 2020-12-24 | B-1 | 17 | 2020-12-28 | 2020-12-31 | Material not drawn | 2021-02-28 | 59
62 | Kabirwala | 002017 | 2020-12-29 | B-1 | 17 | 2020-12-30 | 2020-12-31 | Material not drawn | 2021-02-28 | 59
63 | Kabirwala | 002018 | 2020-12-29 | B-1 | 17 | 2020-12-30 | 2020-12-31 | Material not drawn | 2021-02-28 | 59
64 | Kabirwala | 003299 | 2020-12-30 | B-1 | 17 | 2020-12-30 | 2020-12-31 | Material not drawn | 2021-02-28 | 59
65 | Kabirwala | 003300 | 2020-12-30 | B-1 | 17 | 2020-12-31 | 2020-12-31 | Material not drawn | 2021-02-28 | 59
66 | Kabirwala | 349 | 2020-12-30 | B-1 | 10 | 2020-12-31 | 2020-12-31 | Material not drawn | 2021-02-28 | 59
67 | Musa Pak | 16033 | 2020-12-28 | B-1 | 17 | 2020-12-28 | 2021-01-01 | Material Required | 2021-02-28 | 58
68 | Musa Pak | 8795 | 2020-12-28 | B-1 | 17 | 2020-12-28 | 2021-01-01 | Material Required | 2021-02-28 | 58
69 | Arifwala | 741/B-1 | 03.12.20 | B-1 | 20 | 04.12.20 | 30.12.20 | Material Allocated SR Prepared | 28.02.21 | 58
70 | Vehari | 15312009181 | 2020-10-24 | B-1 | 19 | 2020-12-31 | 2021-01-04 | Allocation Awaited | 2021-02-28 | 55
71 | Pakpattan | 954/BI | 24.11.20 | B-1 | 18.95 |  | 07.12.20 | Material allocated vide No.5087 dt 04.02.2021 work under process | 28.02.21 | 55
72 | Khanpur | 15624009488 | 22.12.2020 | B-1 | 19 | - | 04.01.2021 | Material Not Allocated | 28.02.2021 | 55
73 | Chishtian | 15831007125 | 18.11.21 | B-1 | 19 | 2021-11-27 | 04.01.21 | Partially Material recently allocated, work under progress | 28.02.21 | 55
74 | Sahiwal-1 | 15514009865 | 30-12-2020 | B-1 | 25 | 31-12-2020 | 2021-01-04 | Material not allocated | 28.02.21 | 55
75 | Shujabad | 15162009841 | 2020-12-06 | B-1 | 19 | 2020-12-18 | 2021-01-05 | Material Required | 2021-02-28 | 54
76 | CCW | 630/B-1 b | 04-12-20 | B-1 | 19 | 08-12-20 | 05-01-21 | Material Required | 28.02.21 | 54
77 | Kabirwala | 002997 | 2020-12-04 | B-1 | 17 | 2020-12-07 | 2021-01-05 | Total Material Required | 2021-02-28 | 54
78 | Rajanpur | 15247003589 | 27.11.2020 | B-1 | 19 | 24.12.20 | 06.01.2021 | Rabbit Conductor Required | 28.02.21 | 53
79 | Kot Addu | 15723008896 | 31.12.2020 | B-1 | 19 |  | 06.01.2021 | 30-Mrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 53
80 | Pakpattan | 955/BI | 25.11.20 | B-1 | 18.95 |  | 10.12.20 | Material allocated vide No.5087 dt 04.02.2021 work under process | 28.02.21 | 52
81 | Liaqatpur | 15631005219 | 20.11.2020 | B-1 | 19 | - | 07.01.2021 | 01 HT SS & 25 KVA T/F, Material not allocated | 28.02.2021 | 52
82 | Sahiwal-1 | 15514009711 | 23-12-2020 | B-1 | 25 | 31-12-2020 | 2021-01-07 | Material not allocated | 28.02.21 | 52
83 | A/Abad | 15333009577 | 2020-12-15 | B-1 | 19 | 2020-12-17 | 2021-01-08 | Material Not Allocated | 2021-02-28 | 51
84 | Kot Addu | 15721006610 | 10.12.2020 | B-1 | 19 |  | 08.01.2021 | 20-Mtrs. 4/C PVC required | 28.02.2021 | 51
85 | Kot Addu | 15724006654 | 09.11.2020 | B-1 | 19 |  | 08.01.2021 | 30-Mrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 51
86 | Sahiwal-1 | 15512008587 | 2020-10-12 | B-1 | 25 | 15-12-2020 | 2021-01-08 | Material not allocated | 28.02.21 | 51
87 | DG Khan | 8366 | 18.12.2020 | B-1 | 16 | 28.12.20 | 12.01.2021 | Total Material is required | 28.02.21 | 50
88 | Muzaffargarh | 15718008212 | 22.12.2021 | B-1 | 19 |  | 11.01.2021 | 4-HT Pole, 1290-Mrs Conductor, 10-Mtrs PVC 4/C required | 28.02.2021 | 48
89 | Muzaffargarh | 15719007738 | 05.01.2021 | B-1 | 19 |  | 11.01.2021 | 350-Mtrs Conductor, 10-Mtrs. 4/C PVC required | 28.02.2021 | 48
90 | Kot Addu | 15721006613 | 10.12.2020 | B-1 | 19 |  | 11.01.2021 | 1-HT Pole, 100-Mrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 48
91 | Shujabad | 15163011226 | 2020-12-04 | B-1 | 15 | 2021-01-06 | 2021-01-12 | Material Required | 2021-02-28 | 47
92 | 2nd Mailsi | 15352007709 | 22.12.2020 | B-1 | 19 | 24.12.2020 | 12.01.21 | Material not allocated | 28.02.21 | 47
93 | Kot Addu | 15722012344 | 30.12.2020 | B-1 | 19 |  | 12.01.2021 | 30-Mrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 47
94 | Kot Addu | 15724005228 | 10.06.2020 | B-1 | 19 |  | 12.01.2021 | 1-HT Pole, 100-Mrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 47
95 | Kot Addu | 15725006453 | 17.12.2020 | B-1 | 19 |  | 12.01.2021 | 1-HT Pole, 30-Mrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 47
96 | HND | 15821003106 | 27.12.20 | B-1 | 20 | 31.12.20 | 12.01.2021 | Partially Material recently allocated, work under progress | 28.02.22 | 47
97 | TSP | 15353007535 | 28.12.20 | B-1 | 19 | 05.01.2021 | 13.01.21 | Material not allocated | 28.02.21 | 46
98 | CCW | 635/B-1 b | 21-12-20 | B-1 | 15 | 29-12-20 | 13-01-21 | Material Required | 28.02.21 | 46
99 | R.Y.Khan | 15614007815 | 18.11.2020 | B-1 | 19 | - | 03.01.2021 | Material Not Allocated | 28.02.2021 | 46
100 | Muzaffargarh | 15712010821 | 16.12.2020 | B-1 | 19 |  | 13.01.2021 | 10-Mtrs. 4/C PVC required | 28.02.2021 | 46
101 | Muzaffargarh | 15713007571 | 15.12.2020 | B-1 | 19 |  | 13.01.2021 | 10-Mtrs. 4/C PVC required | 28.02.2021 | 46
102 | Kabirwala | 002044 | 2021-01-06 | B-1 | 24 | 2021-01-07 | 2021-01-13 | Total Material Required | 2021-02-28 | 46
103 | Kabirwala | 003382 | 2021-01-11 | B-1 | 17 | 2021-01-12 | 2021-01-13 | Total Material Required | 2021-02-28 | 46
104 | SWL-II | 6574/B-I | 2021-01-11 | B-1 | 18.609 | 2021-01-11 | 2021-01-15 | allocation awaited | 28.02.21 | 45
105 | M/Channu | 1063/B-1 | 2021-01-07 | B-1 | 23 | 2021-01-14 | 2021-01-14 | Total Material Required | 2021-02-28 | 45
106 | Pakpattan | 958/BI | 07.12.20 | B-1 | 18.65 |  | 18.12.20 | Material allocated vide No.5087 dt 04.02.2021 work under process | 28.02.21 | 44
107 | CCW | 633/B-1 b | 10-12-20 | B-1 | 19 | 16-12-20 | 15-01-21 | Material Required | 28.02.21 | 44
108 | 1st Mailsi | 15351008427 | 18.12.2020 | B-1 | 19 | 22.12.2020 | 18.01.21 | Material not allocated | 28.02.21 | 41
109 | Liaqatpur | 15634004869 | 06.01.2021 | B-1 | 19 | - | 18.01.2021 | 02 HT SS 40', 01 HT SS 36' & 25 KVA T/F, Material not allocated | 28.02.2021 | 41
110 | Layyah | 15735011577 | 23.12.2020 | B-1 | 19 |  | 18.01.2021 | 4-HT Poles, 1519-Mtrs Conductor & 20-Mtrs PVC 4/C required | 28.02.2021 | 41
111 | Sahiwal-1 | 15516007921 | 16-12-2020 | B-1 | 25 | 23-12-2020 | 2021-01-18 | Material not allocated | 28.02.21 | 41
112 | Rajanpur | 15244005173 | 27.11.2020 | B-1 | 19 | 24.12.20 | 19.01.2021 | Rabbit Conductor Required | 28.02.21 | 40
113 | SWL-II | 3793/B-I | 2021-01-15 | B-1 | 18.62 | 2021-01-19 | 2021-01-20 | allocation awaited | 28.02.21 | 40
114 | Layyah | 15731012404 | 12.12.2020 | B-1 | 19 |  | 19.01.2021 | 1-HT Pole, 289-Mtrs Conductor & 20-Mtrs PVC 4/C required | 28.02.2021 | 40
115 | Vehari | 15312009801 | 2021-01-07 | B-1 | 19 | 2021-01-13 | 2021-01-20 | Allocation Awaited | 2021-02-28 | 39
116 | A/Abad | 15333009669 | 2020-12-24 | B-1 | 15 | 2021-01-12 | 20-01-21 | Material Not Allocated | 2021-02-28 | 39
117 | City | 15331005308 | 2021-01-13 | B-1 | 19 | 2021-01-15 | 20-01-21 | Material Not Allocated | 2021-02-28 | 39
118 | City Bwp | 15416010034 613 | 09.11.2020 | B-1 | 1900-01-18 | 08.12.2020 | 23.12.2020 | under progress | 28.02.2021 | 39
119 | APEast | 3249 | 08.01.21 | B-1 | 1900-01-18 | 13.01.21 | 2021-01-20 | Not Allocate | 2021-02-28 | 39
120 | APEast | 7937 | 23.12.20 | B-1 | 1900-01-18 | 29.12.20 | 2021-01-20 | Not Allocate | 2021-02-28 | 39
121 | Hasilpur | 15454005269 | 12.01.21 | B-1 | 19 | 19.01.21 | 44216 | Material not allocated | 2021-02-28 | 39
122 | Khanpur | 15623006776 | 28.12.2020 | B-1 | 19 | - | 20.01.2021 | Material Not Allocated | 28.02.2021 | 39
123 | Muzaffargarh | 15718008341 | 05.01.2021 | B-1 | 19 |  | 20.01.2021 | 2-HT Pole, 650-Mrs Conductor, 10-Mtrs PVC 4/C required | 28.02.2021 | 39
124 | Kabirwala | 003395 | 2021-01-12 | B-1 | 17 | 2021-01-12 | 2021-01-20 | Total Material Required | 2021-02-28 | 39
125 | R.Y.Khan | 15614007923 | 01.12.2020 | B-1 | 19 | - | 21.01.2021 | Material Not Allocated | 28.02.2021 | 38
126 | BWN | 15812004630 | 21.12.20 | B-1 | 20 | 19.01.21 | 22.01.21 | Partially Material recently allocated, work under progress | 28.02.21 | 38
127 | BWN | 15816002804 | 16.01.21 | B-1 | 20 | 21.01.21 | 22.01.21 | Partially Material recently allocated, work under progress | 28.02.21 | 38
128 | R.Y.Khan | 15612009184 | 12.01.2021 | B-1 | 19 | - | 22.01.2021 | Material Not Allocated | 28.02.2021 | 37
129 | HND | 15822002733 | 26.12.20 | B-1 | 20 | 31.12.20 | 22.01.2021 | Partially Material recently allocated, work under progress | 28.02.23 | 37
130 | Chishtian | 15831007520 | 30.12.20 | B-1 | 20 | 2021-01-18 | 23.01.21 | Partially Material recently allocated, work under progress | 28.02.21 | 36
131 | Pakpattan | 956/BI | 25.11.20 | B-1 | 18.95 |  | 28.12.20 | Material allocated vide No.5087 dt 04.02.2021 work under process | 28.02.21 | 34
132 | CCW | 637/B-1 b | 09-01-21 | B-1 | 19 | 19-01-21 | 25-01-21 | Material Required | 28.02.21 | 34
133 | R.Y.Khan | 15613010082 | 18.01.2021 | B-1 | 19 | - | 25.01.2021 | Material Not Allocated | 28.02.2021 | 34
134 | Sadiqabad | 15643006501 | 30.12.2020 | B-1 | 19 | - | 25.01.2021 | Material Not Allocated | 28.02.2021 | 34
135 | Kot Addu | 15724007064 | 06.01.2021 | B-1 | 19 |  | 25.01.2021 | 30-Mrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 34
136 | Khanewal | 15912003210 | 2020-12-31 | B-1 | 16 | 2021-01-04 | 2021-01-25 | Total Material Required | 2021-02-28 | 34
137 | Sahiwal-1 | 15513011281 | 14-01-2021 | B-1 | 25 | 20-01-2021 | 2021-01-25 | Material not allocated | 28.02.21 | 34
138 | Sahiwal-1 | 15516008145 | 14-01-2021 | B-1 | 25 | 20-01-2021 | 2021-01-25 | Material not allocated | 28.02.21 | 34
139 | Cantt | 15113007967 | 2021-01-05 | B-1 | 5 | 2021-01-20 | 2021-01-26 | Material Required | 2021-02-28 | 33
140 | Cantt | 15113008079 | 2021-01-21 | B-1 | 5 | 2021-01-26 | 2021-01-26 | Material Required | 2021-02-28 | 33
141 | Vehari | 15311012204 | 2021-01-22 | B-1 | 19 | 2021-01-22 | 2021-01-26 | Allocation Awaited | 2021-02-28 | 33
142 | Vehari | 15312009665 | 2020-12-17 | B-1 | 19 | 2021-01-21 | 2021-01-26 | Allocation Awaited | 2021-02-28 | 33
143 | SWL-II | 7581-B-I | 2021-01-14 | B-1 | 18.85 | 2021-01-19 | 2021-01-27 | allocation awaited | 28.02.21 | 33
144 | Muzaffargarh | 15718008429 | 14.01.2021 | B-1 | 19 |  | 26.01.2021 | 10-Mtrs. 4/C PVC required | 28.02.2021 | 33
145 | Kabirwala | 003351 | 2021-01-19 | B-1 | 17 | 2021-01-20 | 2021-01-26 | Total Material Required | 2021-02-28 | 33
146 | M/Channu | 1066/B-1 | 2021-01-26 | B-1 | 19 | 2021-01-26 | 2021-01-26 | Total Material Required | 2021-02-28 | 33
147 | Shujabad | 15162010223 | 2021-01-07 | B-1 | 19 | 2021-01-20 | 2021-01-27 | Material Required | 2021-02-28 | 32
148 | S.R.Alam | 15193003666/570 | 2020-12-04 | B-1 | 5 | 2021-01-22 | 2021-01-27 | Material Required | 2021-02-28 | 32
149 | kot chutta | 9929 | 09.01.2021 | B-1 | 19 | 16.01.21 | 26.01.20201 | Rabbit Conductor Required | 28.02.21 | 32
150 | Liaqatpur | 15633007538 | 08.01.2021 | B-1 | 19 | - | 27.01.2021 | 25 KVA T/F Meter Material not allocated | 28.02.2021 | 32
151 | Ali Pur | 15744009050 | 11.01.2021 | B-1 | 19 |  | 27.01.2021 | 10-Mtrs. 4/C PVC required | 28.02.2021 | 32
152 | Khanewal | 15912003288 | 2021-12-01 | B-1 | 16 | 2021-01-22 | 2021-01-27 | Total Material Required | 2021-02-28 | 32
153 | Kabirwala | 003427 | 2021-01-18 | B-1 | 16 | 2021-01-20 | 2021-01-27 | Total Material Required | 2021-02-28 | 32
154 | Sahiwal-1 | 15512008702 | 29-12-2020 | B-1 | 25 | 31-12-2020 | 2021-01-26 | Material not allocated | 28.02.21 | 32
155 | Mumtazabad | 15127004402/2478 | 2021-01-15 | B-1 | 17 | 2021-01-25 | 2021-01-28 | Material Required | 2021-02-28 | 31
156 | S.R.Alam | 15192010761/569 | 2021-01-12 | B-1 | 17 | 2021-01-20 | 2021-01-28 | Material Required | 2021-02-28 | 31
157 | DG Khan | 8628 | 21.01.2021 | B-1 | 19 | 04.01.21 | 27.01.2021 | Rabbit Conductor Required | 28.02.21 | 31
158 | Model Town | 15442010489/B1 | 28.01.2021 | B-1 | 19 | 28.01.2021 | 30.01.2021 | Total material required. | 28-02-2021 | 31
159 | Hasilpur | 15452007535 | 24.01.21 | B-1 | 19 | 27.01.21 | 2021-01-28 | Material not allocated | 2021-02-28 | 31
160 | K/Pacca | 15464004523 | 1/13/2021 | B-1 | 23 | 2021-01-13 | 2021-01-28 | Material not allocate | 2021-02-28 | 31
161 | Sadiqabad | 15645000862 | 19.01.2021 | B-1 | 19 | - | 28.01.2021 | Material Not Allocated | 28.02.2021 | 31
162 | Kot Addu | 15725006404 | 10.12.2020 | B-1 | 19 |  | 28.01.2021 | 1-HT Pole, 160-Mrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 31
163 | Layyah | 15734009050 | 19.01.2021 | B-1 | 19 |  | 28.01.2021 | 1-HT Pole, 347-Mtrs Conductor, 20-Mtrs PVC 4/C required | 31.12.2021 | 31
164 | Layyah | 15734009037 | 28.01.2021 | B-1 | 19 |  | 28.01.2021 | 2-HT Pole, 654-Mtrs Conductor & 20-Mtrs PVC 4/C required | 28.02.2021 | 31
165 | Ali Pur | 15741011109 | 26.01.2021 | B-1 | 19 |  | 28.01.2021 | 10-Mtrs. 4/C PVC required | 28.02.2021 | 31
166 | Kabirwala | 002074 | 2021-01-19 | B-1 | 17 | 2021-01-20 | 2021-01-28 | Total Material Required | 2021-02-28 | 31
167 | Kabirwala | 003414 | 2021-01-26 | B-1 | 16 | 2021-01-27 | 2021-01-28 | Total Material Required | 2021-02-28 | 31
168 | Mumtazabad | 15127004413/2480 | 2021-01-21 | B-1 | 25 | 2021-01-25 | 2021-01-29 | Material Required | 2021-02-28 | 30
169 | Shujabad | 15163011565 | 2021-01-15 | B-1 | 19 | 2021-01-20 | 2021-01-29 | Material Required | 2021-02-28 | 30
170 | DG Khan | 9073 | 21.01.2021 | B-1 | 19 | 04.01.21 | 28.01.2021 | Rabbit Conductor Required | 28.02.21 | 30
171 | kot chutta | 9909 | 06.01.2021 | B-1 | 19 | 10.01.21 | 28.01.2021 | Rabbit Conductor Required | 28.02.21 | 30
172 | kot chutta | 6402 | 27.01.2021 | B-1 | 19 | 29.01.21 | 29.01.2021 | Rabbit Conductor Required | 28.02.21 | 30
173 | kot chutta | 5575 | 15.01.2021 | B-1 | 19 | 19.01.21 | 29.01.2021 | Rabbit Conductor Required | 28.02.21 | 30
174 | TAUNSA | 15263003993 | dt. 25.1.21 | B-1 | 18 | 26.01.21 | 29.01.21 | Total Material Required | 28.02.21 | 30
175 | M/Town | 15334008271 | 2020-10-20 | B-1 | 5 | 2021-01-29 | 2021-01-29 | Material Not Allocated | 2021-02-28 | 30
176 | CCW | 638/B-1 b | 12-01-21 | B-1 | 13 | 19-01-21 | 29-01-21 | Material Required | 28.02.21 | 30
177 | R.Y.Khan | 15613010161 | 22.01.2021 | B-1 | 19 | - | 29.01.2021 | Material Not Allocated | 28.02.2021 | 30
178 | Layyah | 15733008071 | 11.01.2021 | B-1 | 19 |  | 29.01.2021 | 4-HT Poles, 1278-Mtrs Conductor, 20-Mtrs PVC 4/C required | 28.02.2021 | 30
179 | Ali Pur | 15742008998 | 26.01.2021 | B-1 | 19 |  | 29.01.2021 | 10-Mtrs. 4/C PVC required | 28.02.2021 | 30
180 | M/Channu | 1064/B-1 | 2021-01-07 | B-1 | 19 | 2021-01-29 | 2021-01-29 | Total Material Required | 2021-02-28 | 30
181 | Muzaffargarh | 15718008569 | 28.01.2021 | B-1 | 19 |  | 30.01.2021 | 10-Mtrs. 4/C PVC required | 28.02.2021 | 29
182 | BWN | 15811004232 | 26.01.21 | B-1 | 20 | 12.02.21 | 18.02.21 | Material demanded | 28.02.21 | 29
183 | BWN | 15814001046 | 20.01.21 | B-1 | 20 | 30.01.21 | 30.01.21 | Partially Material recently allocated, work under progress | 28.02.21 | 29
184 | Kabirwala | 003380 | 2021-01-11 | B-1 | 17 | 2021-01-12 | 2021-01-30 | Total Material Required | 2021-02-28 | 29
185 | R.Y.Khan | 15612009413 | 29.01.2021 | B-1 | 19 | - | 01.02.2021 | Material Not Allocated | 28.02.2021 | 28
186 | M/Channu | 1065/B-1 | 22.01.21 | B-1 | 19 | 27.01.21 | 01.02.21 | Total Material Required | 2021-02-28 | 27
187 | Vehari | 15313011027 | 2021-01-19 | B-1 | 19 | 2021-01-19 | 2021-02-02 | Allocation Awaited | 2021-02-28 | 26
188 | Arifwala | 744/B-1 | 07.12.20 | B-1 | 20 | 09.12.20 | 04.01.21 | Allocation of Material Awaited | 28.02.21 | 26
189 | SWL-II | 7482/B-I | 2021-01-01 | B-1 | 18.85 | 2021-01-08 | 2021-02-03 | allocation awaited | 28.02.21 | 26
190 | Kot Addu | 15725006874 | 27.01.2021 | B-1 | 19 |  | 02.02.2021 | Material allocation awaited | 28.02.2021 | 26
191 | Mumtazabad | 15128008959/2481 | 21.01.21 | B-1 | 17 | 2021-01-26 | 2021-02-03 | Material Required | 2021-02-28 | 25
192 | Kahror Pacca | 15464004511 | 2021-04-01 | B-1 | 19 | 2021-01-04 | 2021-02-03 | Material not allocate | 2021-02-28 | 25
193 | Arifwala | 750/B-1 | 11.01.21 | B-1 | 20 | 12.01.21 | 03.02.21 | Allocation of Material Awaited | 28.02.21 | 25
194 | Arifwala | 757/B-1 | 01.02.21 | B-1 | 4.9 | 02.02.21 | 03.02.21 | Allocation of Material Awaited | 28.02.21 | 25
195 | Kot Addu | 15724007247 | 26.01.2021 | B-1 | 19 |  | 03.02.2021 | Material allocation awaited | 28.02.2021 | 25
196 | M/Channu | 1061/B-1 | 08.12.20 | B-1 | 19 | 07.01.21 | 03.02.21 | Total Material Required | 2021-02-28 | 25
197 | S.R.Alam | 15195008346/564 | 2021-01-07 | B-1 | 5 | 2021-01-07 | 2021-02-04 | Material Required | 2021-02-28 | 24
198 | Vehari | 15311012051 | 2021-01-08 | B-1 | 19 | 2021-01-28 | 2021-02-04 | Allocation Awaited | 2021-02-28 | 24
199 | City Bwp | 15414009439 615 | 16.12.2020 | B-1 | 19 | 02.02.2021 | 04.02.2021 | Material required | 28.02.2021 | 24
200 | Arifwala | 755/B-1 | 26.01.21 | B-1 | 14.92 | 27.01.21 | 04.02.21 | Allocation of Material Awaited | 28.02.21 | 24
201 | Khanewal | 15915001954 | 2021-01-07 | B-1 | 16 | 2021-01-15 | 2021-02-04 | Total Material Required | 2021-02-28 | 24
202 | Kabirwala | 002106 | 2021-01-28 | B-1 | 16 | 2021-01-29 | 2021-02-04 | Total Material Required | 2021-02-28 | 24
203 | Arifwala | 754/B-1 | 20.01.21 | B-1 | 18.65 | 21.01.21 | 08.02.21 | Allocation of Material Awaited | 28.02.21 | 22
204 | S.R.Alam | 15192010416/555 | 2020-12-09 | B-1 | 24 | 2021-01-07 | 2021-02-08 | Material Required | 2021-02-28 | 20
205 | DG Khan | 10855 | 13.01.21 | B-1 | 17 | 01.02.21 | 08.02.21 | Total Material is required | 28.02.21 | 20
206 | TAUNSA | 15263004028 | 03.02.21 | B-1 | 18 | 05.02.21 | 10.02.21 | Total Material is required | 28.02.21 | 20
207 | Liaqat Pur | 15631005626 | 18.01.2021 | B-1 | 19 | - | 08.02.2021 | 01 HT SS & 25 KVA T/F | 28.02.2021 | 20
208 | Kot Addu | 15723008548 | 02.12.2020 | B-1 | 19 |  | 08.02.2021 | Material allocation awaited | 28.02.2021 | 20
209 | Kabirwala | 003411 | 2021-01-26 | B-1 | 16 | 2021-01-27 | 2021-02-08 | Total Material Required | 2021-02-28 | 20
210 | Mumtazabad | 15125009213/2484 | 29.01.21 | B-1 | 5 | 2021-02-03 | 2021-02-09 | Material Required | 2021-02-28 | 19
211 | City | 15132011161 | 2021-01-15 | B-1 | 16 | 2021-02-02 | 2021-02-09 | Material Required | 2021-02-28 | 19
212 | City | 15133003236 | 2021-01-01 | B-1 | 24 | 2021-01-13 | 2021-02-09 | Material Required | 2021-02-28 | 19
213 | Pakpattan | 965 | 01.02.21 | B-1 | 19 |  | 09.02.2021 | allocation awaited | 28.02.21 | 19
214 | City | 15132011241 | 2021-02-02 | B-1 | 5 | 2021-02-08 | 2021-02-10 | Material Required | 2021-02-28 | 18
215 | Vehari | 15314008770 | 2021-01-13 | B-1 | 19 | 2021-02-04 | 2021-02-10 | Allocation Awaited | 2021-02-28 | 18
216 | APEast | 5050 | 02.02.21 | B-1 | 19 | 08.02.21 | 2021-02-10 | Not Allocate | 2021-02-28 | 18
217 | City | 15132011146 | 2021-01-26 | B-1 | 5 | 2021-02-02 | 2021-02-11 | Material Required | 2021-02-28 | 17
218 | DG Khan | 6096 | 09.02.21 | B-1 | 19 | 10.02.21 | 11.02.21 | Total Material is required | 28.02.21 | 17
219 | A/Abad | 15333010078 | 2021-01-27 | B-1 | 19 | 2021-01-27 | 2021-02-11 | Material Not Allocated | 2021-02-28 | 17
220 | Hasilpur | 15452007523 | 22.01.21 | B-1 | 20 | 26.01.21 | 2021-02-11 | Material not allocated | 2021-02-28 | 17
221 | City Bwp | 15416010052 614 | 13.11.2020 | B-1 | 1900-01-18 | 07.12.2020 | 14.01.2021 | Material required | 28.02.2021 | 17
222 | Arifwala | 758/B-1 | 02.02.21 | B-1 | 20 | 08.02.21 | 11.02.21 | Allocation of Material Awaited | 28.02.21 | 17
223 | Arifwala | 760/B-1 | 04.02.21 | B-1 | 20 | 08.02.21 | 11.02.21 | Allocation of Material Awaited | 28.02.21 | 17
224 | Arifwala | 761/B-1 | 08.02.21 | B-1 | 19 | 10.02.21 | 11.02.21 | Allocation of Material Awaited | 28.02.21 | 17
225 | CCW | 641/B-1 b | 27-01-21 | B-1 | 19 | 01-02-21 | 11-02-21 | Material Required | 28.02.21 | 17
226 | SWL-II | 6499/B-I | 2021-01-06 | B-1 | 18.85 | 2021-01-12 | 2021-02-12 | allocation awaited | 28.02.21 | 17
227 | Sadiqabad | 15643006532 | 05.01.2021 | B-1 | 19 | - | 11.02.2021 | Material Not Allocated | 28.02.2021 | 17
228 | Mumtazabad | 15127004437/2482 | 25.01.21 | B-1 | 25 | 2021-01-28 | 2021-02-12 | Material Required | 2021-02-28 | 16
229 | Shujabad | 15161010841 | 2021-01-29 | B-1 | 19 | 01-02-21 | 2021-02-12 | Material Required | 2021-02-28 | 16
230 | Arifwala | 751/B-1 | 11.01.21 | B-1 | 20 | 12.01.21 | 12.02.21 | Allocation of Material Awaited | 28.02.21 | 16
231 | Kot Addu | 15723009465 | 09.02.2021 | B-1 | 19 |  | 12.02.2021 | Material allocation awaited | 28.02.2021 | 16
232 | Alipur | 15741011117 | 02.02.2021 | B-1 | 19 |  | 12.02.2021 | Material Allocation awaited | 28.02.2021 | 16
233 | BWN | 15813004190 | 15.12.20 | B-1 | 20 | 19.01.21 | 19.02.21 | Material demanded | 28.02.21 | 16
234 | S.R.Alam | 15192011038/575 | 2021-02-09 | B-1 | 25 | 2021-02-12 | 2021-02-15 | Material Required | 2021-02-28 | 13
235 | 2nd Mailsi | 15352008054 | 2021-02-04 | B-1 | 19 | 10.02.21 | 15.02.21 | Material Not Allocated | 28.02.21 | 13
236 | Alipur | 15744009225 | 02.02.2021 | B-1 | 19 |  | 15.02.2021 | Material Allocation awaited | 28.02.2021 | 13
237 | Chishtian | 15836003516/B1 | 2021-01-28 | B-1 | 20 | 2021-02-12 | 15.02.21 | Material demanded | 28.02.21 | 13
238 | Khanewal | 15912003438 | 2021-01-27 | B-1 | 16 | 2021-02-09 | 2021-02-15 | Total Material Required | 2021-02-28 | 13
239 | Mumtazabad | 15128009132/2485 | 08.02.21 | B-1 | 16 | 2021-02-15 | 2021-02-16 | Material Required | 2021-02-28 | 12
240 | Arifwala | 756/B-1 | 26.01.21 | B-1 | 14.92 | 27.01.21 | 16.02.21 | Allocation of Material Awaited | 28.02.21 | 12
241 | Sadiqabad | 15641011608 | 04.02.2021 | B-1 | 19 | - | 16.02.2021 | Material Not Allocated | 28.02.2021 | 12
242 | Sadiqabad | 15645000805 | 08.01.2021 | B-1 | 19 | - | 16.02.2021 | Material Not Allocated | 28.02.2021 | 12
243 | Alipur | 15744009226 | 02.02.2021 | B-1 | 19 |  | 16.02.2021 | Material Allocation awaited | 28.02.2021 | 12
244 | Mumtazabad | 15125009260/2487 | 02.02.21 | B-1 | 5 | 2021-02-16 | 2021-02-17 | Material Required | 2021-02-28 | 11
245 | Shujabad | 15162010482 | 2021-02-08 | B-1 | 19 | 12-02-21 | 2021-02-17 | Material Required | 2021-02-28 | 11
246 | Musa Pak | 15174009364 | 2021-02-15 | B-1 | 8 | 2021-02-17 | 2021-02-17 | Material Required | 2021-02-28 | 11
247 | CCW | 640/B-1 b | 25-01-21 | B-1 | 19 | 27-01-21 | 17-02-21 | Material Required | 28.02.21 | 11
248 | Khanewal | 15912003630 | 2021-02-09 | B-1 | 16 | 2021-02-15 | 2021-02-17 | Total Material Required | 2021-02-28 | 11
249 | Kabirwala | 003563 | 2021-02-04 | B-1 | 17 | 2021-02-08 | 2021-02-17 | Total Material Required | 2021-02-28 | 11
250 | Kabirwala | 003587 | 2021-02-09 | B-1 | 17 | 2021-02-12 | 2021-02-17 | Total Material Required | 2021-02-28 | 11
251 | Mumtazabad | 15121009619/2488 | 12.02.21 | B-1 | 5 | 2021-02-17 | 2021-02-18 | Material Required | 2021-02-28 | 10
252 | City | 15132011363 | 2021-02-10 | B-1 | 5 | 2021-02-18 | 2021-02-18 | Material Required | 2021-02-28 | 10
253 | S.R.Alam | 15194003483/572 | 2020-12-24 | B-1 | 5 | 2021-12-24 | 2021-02-18 | Material Required | 2021-02-28 | 10
254 | S.R.Alam | 15192010983/574 | 2021-02-03 | B-1 | 24 | 2021-02-12 | 2021-02-18 | Material Required | 2021-02-28 | 10
255 | APEast | 8281 | 08.02.21 | B-1 | 19 | 09.02.21 | 2021-02-18 | Not Allocate | 2021-02-28 | 10
256 | Sadiqabad | 15644009586 | 11.01.2021 | B-1 | 19 | - | 18.02.2021 | Material Not Allocated | 28.02.2021 | 10
257 | Muzaffargarh | 15711007245 | 12.02.2021 | B-1 | 19 |  | 18.02.2021 | Material allocation awaited | 28.02.2021 | 10
258 | Kot Addu | 15724007427 | 10.02.2021 | B-1 | 19 |  | 18.02.2021 | Material allocation awaited | 28.02.2021 | 10
259 | Shujabad | 15164011319 | 2021-01-28 | B-1 | 19 | 01-02-21 | 2021-02-19 | Material Required | 2021-02-28 | 9
260 | S.R.Alam | 15191012181/573 | 2021-01-12 | B-1 | 5 | 2021-02-10 | 2021-02-19 | Material Required | 2021-02-28 | 9
261 | APEast | 9518 | 11.02.21 | B-1 | 19 | 15.02.21 | 2021-02-19 | Not Allocate | 2021-02-28 | 9
262 | Arifwala | 748/B-1 | 04.01.21 | B-1 | 18.65 | 06.01.21 | 21.01.21 | Allocation of Material Awaited | 28.02.21 | 9
263 | CCW | 642/B-1 b | 08-02-21 | B-1 | 19 | 17-02-21 | 19-02-21 | Material Required | 28.02.21 | 9
264 | SWL-II | 6952/B-I | 2021-02-20 | B-1 | 17.35 | 2021-02-24 | 2021-02-20 | allocation awaited | 28.02.21 | 9
265 | Liaqatpur | 15631005607 | 18.01.2021 | B-1 | 19 | - | 19.02.2021 | 01 HT SS & 25 KVA T/F | 28.02.2021 | 9
266 | Sadiqabad | 15644009746 | 22.01.2021 | B-1 | 19 | - | 19.02.2021 | Material Not Allocated | 28.02.2021 | 9
267 | HND | 15821003295 | 11.02.21 | B-1 | 20 | 15.02.2021 | 19.02.2021 | Material demanded | 28.02.21 | 9
268 | Muzaffargarh | 15711007093 | 19.01.2021 | B-1 | 19 |  | 22.02.2021 | Material allocation awaited | 28.02.2021 | 8
269 | City | 15132010728 | 2020-12-21 | B-1 | 5 | 2021-02-17 | 2021-02-22 | Material Required | 2021-02-28 | 6
270 | DG Khan | 10901 | 01.02.21 | B-1 | 19 | 17.02.21 | 22.02.21 | Total Material is required | 28.02.21 | 6
271 | Model Town | 15442010384/B1 | 08.01.2021 | B-1 | 19 | 08.01.2021 | 22.02.2021 | Total material required. | 28-02-2021 | 6
272 | Pakpattan | 960/BI | 16.01.21 | B-1 | 19 |  | 25.01.21 | allocation awaited | 28.02.21 | 6
273 | Pakpattan | 962/BI | 18.01.21 | B-1 | 19 |  | 25.01.21 | allocation awaited | 28.02.21 | 6
274 | Arifwala | 763/B-1 | 10.02.21 | B-1 | 14.92 | 16.02.21 | 22.02.21 | Allocation of Material Awaited | 28.02.21 | 6
275 | Arifwala | 764/B-1 | 17.02.21 | B-1 | 20 | 18.02.21 | 22.02.21 | Allocation of Material Awaited | 28.02.21 | 6
276 | R.Y.Khan | 15614008799 | 16.02.2021 | B-1 | 19 | - | 22.02.2021 | Material Not Allocated | 28.02.2021 | 6
277 | Liaqatpur | 15634005039 | 03.02.2021 | B-1 | 19 | - | 22.02.2021 | 25 KVA T/F Meter | 28.02.2021 | 6
278 | Sadiqabad | 15645000956 | 12.02.2021 | B-1 | 19 | - | 22.02.2021 | Material Not Allocated | 28.02.2021 | 6
279 | Layyah | 15731012862 | 12.01.2021 | B-1 | 19 |  | 22.02.2021 | Material allocation awaited | 28.02.2021 | 6
280 | Layyah | 15734009091 | 27.01.2021 | B-1 | 19 |  | 22.02.2021 | Material allocation awaited | 28.02.2021 | 6
281 | Alipur | 15741011283 | 15.02.2021 | B-1 | 19 |  | 22.02.2021 | Material Allocation awaited | 28.02.2021 | 6
282 | HND | 15824003617 | 15.02.21 | B-1 | 20 | 15.02.2021 | 22.02.2021 | Material demanded | 28.02.21 | 6
283 | Kabirwala | 002206 | 2021-02-16 | B-1 | 17 | 2021-02-18 | 2021-02-22 | Total Material Required | 2021-02-28 | 6
284 | M/Channu | 1069/B-1 | 22.02.21 | B-1 | 16 | 22.02.21 | 22.02.21 | Total Material Required | 2021-02-28 | 6
285 | Mumtazabad | 15121009413/2483 | 26.01.21 | B-1 | 25 | 2021-01-28 | 2021-02-23 | Material Required | 2021-02-28 | 5
286 | Musa Pak | 15173014154 | 2021-01-04 | B-1 | 5 | 2021-02-18 | 2021-02-23 | Material Required | 2021-02-28 | 5
287 | Model Town | 15442010535/B1 | 04.02.2021 | B-1 | 19 | 09.02.2021 | 23.02.2021 | Total material required. | 28-02-2021 | 5
288 | Kahror Pacca | 15465005608 | 2021-02-02 | B-1 | 19 | 2021-02-12 | 2021-02-23 | Material not allocate | 2021-02-28 | 5
289 | Arifwala | 753/B-1 | 18.01.21 | B-1 | 20 | 19.01.21 | 25.01.21 | Allocation of Material Awaited | 28.02.21 | 5
290 | CCW | 643/B-1 b | 15-02-21 | B-1 | 13 | 22-02-21 | 23-02-21 | Material Required | 28.02.21 | 5
291 | Layyah | 15732014903 | 13.01.2021 | B-1 | 19 |  | 23.02.2021 | Material allocation awaited | 28.02.2021 | 5
292 | Alipur | 15742009262 | 15.02.2021 | B-1 | 19 |  | 23.02.2021 | Material Allocation awaited | 28.02.2021 | 5
293 | Alipur | 15743009690 | 17.02.2021 | B-1 | 19 |  | 23.02.2021 | Material Allocation awaited | 28.02.2021 | 5
294 | Kabirwala | 003527 | 2021-02-09 | B-1 | 25 | 2021-02-12 | 2021-02-23 | Total Material Required | 2021-02-28 | 5
295 | Kabirwala | 003633 | 2021-02-18 | B-1 | 17 | 2021-02-18 | 2021-02-23 | Total Material Required | 2021-02-28 | 5
296 | M/Channu | 1068/B-1 | 09.02.21 | B-1 | 22 | 09.02.21 | 23.02.21 | Total Material Required | 2021-02-28 | 5
297 | Cantt | 15117002576 | 2021-01-04 | B-1 | 5 | 2021-02-20 | 2021-02-24 | Material Required | 2021-02-28 | 4
298 | Mumtazabad | 15121009690/2491 | 17.02.21 | B-1 | 8 | 2021-02-22 | 2021-02-24 | Material Required | 2021-02-28 | 4
299 | Mumtazabad | 15127004337/2489 | 28.12.20 | B-1 | 8 | 2021-02-18 | 2021-02-24 | Material Required | 2021-02-28 | 4
300 | City | 15132011276 | 2021-02-04 | B-1 | 5 | 2021-02-18 | 2021-02-24 | Material Required | 2021-02-28 | 4
301 | Musa Pak | 15173014885 | 2021-02-16 | B-1 | 17 | 2021-02-23 | 2021-02-24 | Material Required | 2021-02-28 | 4
302 | Kahror Pacca | 15461005906 | 2/17/2021 | B-1 | 19 | 2021-02-18 | 2021-02-24 | Material not allocate | 2021-02-28 | 4
303 | Arifwala | 752/B-1 | 15.01.21 | B-1 | 18.65 | 19.01.21 | 27.01.21 | Allocation of Material Awaited | 28.02.21 | 4
304 | Arifwala | 759/B-1 | 04.02.21 | B-1 | 20 | 08.02.21 | 24.02.21 | Allocation of Material Awaited | 28.02.21 | 4
305 | SWL-II | 3985/ B-II | 2021-02-22 | B-1 | 47 | 2021-02-24 | 2021-02-25 | allocation awaited | 28.02.21 | 4
306 | Alipur | 15744009415 | 16.02.2021 | B-1 | 19 |  | 24.02.2021 | Material Allocation awaited | 28.02.2021 | 4
307 | Mumtazabad | 15121009618/2490 | 12.02.21 | B-1 | 13 | 2021-02-18 | 2021-02-25 | Material Required | 2021-02-28 | 3
308 | Mumtazabad | 15127004403/2479 | 15.01.21 | B-1 | 17 | 2021-01-25 | 2021-02-25 | Material Required | 2021-02-28 | 3
309 | Musa Pak | 15173014790 | 2021-02-10 | B-1 | 17 | 2021-02-23 | 2021-02-25 | Material Required | 2021-02-28 | 3
310 | S.R.Alam | 15194003482/571 | 2020-12-24 | B-1 | 5 | 2021-12-24 | 2021-02-25 | Material Required | 2021-02-28 | 3
311 | kot chutta | 6106 | 21.01.21 | B-1 | 19 | 01.02.21 | 25.02.21 | Total Material is required | 28.02.21 | 3
312 | Vehari | 15313011206 | 2021-02-01 | B-1 | 19 | 2021-02-17 | 2021-02-25 | Allocation Awaited | 2021-02-28 | 3
313 | City Bwp | 15416010940 616 | 26.01.2021 | B-1 | 19 | 23.02.2021 | 25.02.2021 | Material required | 28.02.2021 | 3
314 | City Bwp | 15411006443 617 | 23.02.2021 | B-1 | 19 | 23.02.2021 | 25.02.2021 | Material required | 28.02.2021 | 3
315 | Hasilpur | 15451006169 | 18.02.21 | B-1 | 19 | 23.02.21 | 2021-02-25 | Material not allocated | 2021-02-28 | 3
316 | Pakpattan | 963/BI | 23.01.21 | B-1 | 19 |  | 28.01.21 | allocation awaited | 28.02.21 | 3
317 | Arifwala | 762/B-1 | 08.02.21 | B-1 | 14.92 | 10.02.21 | 25.02.21 | Allocation of Material Awaited | 28.02.21 | 3
318 | CCW | 639/B-1 b | 25-01-21 | B-1 | 17 | 27-01-21 | 25-02-21 | Material Required | 28.02.21 | 3
319 | Liaqatpur | 15632005160 | 10.02.2021 | B-1 | 19 | - | 25.02.2021 | 25 KVA T/F Meter | 28.02.2021 | 3
320 | Sadiqabad | 15643006501 | 30.12.2020 | B-1 | 19 | - | 25.01.2021 | Test Report Under Verification | 28.02.2021 | 3
321 | Sadiqabad | 15464009869 | 04.02.2021 | B-1 | 19 | - | 25.02.2021 | Material Not Allocated | 28.02.2021 | 3
322 | Kot Addu | 15725007123 | 18.02.2021 | B-1 | 19 |  | 25.02.2021 | Material allocation awaited | 28.02.2021 | 3
323 | Kot Addu | 15725007095 | 16.02.2021 | B-1 | 19 |  | 25.02.2021 | Material allocation awaited | 28.02.2021 | 3
324 | Layyah | 15731013361 | 05.02.2021 | B-1 | 19 |  | 25.02.2021 | Material allocation awaited | 28.02.2021 | 3
325 | Layyah | 15732015219 | 27.01.2021 | B-1 | 19 |  | 25.02.2021 | Material allocation awaited | 28.02.2021 | 3
326 | Alipur | 15744009227 | 02.02.2021 | B-1 | 19 |  | 25.02.2021 | Material Allocation awaited | 28.02.2021 | 3
327 | Alipur | 15744009505 | 22.02.2021 | B-1 | 19 |  | 25.02.2021 | Material Allocation awaited | 28.02.2021 | 3
328 | BWN | 15814001184 | 03.02.21 | B-1 | 20 | 19.02.21 | 25.02.21 | Material demanded | 28.02.21 | 3
329 | BWN | 15816002949 | 10.02.21 | B-1 | 20 | 24.02.21 | 25.02.21 | Material demanded | 28.02.21 | 3
330 | Kabirwala | 003666 | 2021-02-22 | B-1 | 16 | 2021-02-23 | 2021-02-25 | Total Material Required | 2021-02-28 | 3
331 | Mumtazabad | 15127004582/2496 | 24.02.21 | B-1 | 8 | 2021-02-25 | 2021-02-26 | Material Required | 2021-02-28 | 2
332 | City | 15133003415 | 2021-02-11 | B-1 | 5 | 2021-02-24 | 2021-02-26 | Material Required | 2021-02-28 | 2
333 | City | 15133003440 | 2021-02-16 | B-1 | 5 | 2021-02-26 | 2021-02-26 | Material Required | 2021-02-28 | 2
334 | Shujabad | 15161011086 | 2021-02-12 | B-1 | 19 | 24-02-21 | 2021-02-26 | Material Required | 2021-02-28 | 2
335 | Shujabad | 15162010566 | 2021-02-26 | B-1 | 19 | 24-02-21 | 2021-02-26 | Material Required | 2021-02-28 | 2
336 | DG Khan | 11342 | 24.02.21 | B-1 | 18 | 25.02.21 | 26.02.21 | Total Material is required | 28.02.21 | 2
337 | TAUNSA | 15265008176 | 23.02.21 | B-1 | 18 | 24.02.21 | 26.02.21 | Total Material is required | 28.02.21 | 2
338 | Mumtazabad | 15128009291/2497 | 24.02.21 | B-1 | 8 | 2021-06-25 | 2021-02-26 | Material Required | 2021-02-28 | 2
339 | Vehari | 15313011374 | 2021-02-10 | B-1 | 19 | 2021-02-19 | 2021-02-26 | Allocation Awaited | 2021-02-28 | 2
340 | 2nd Mailsi | 15352008077 | 2021-02-10 | B-1 | 19 | 24.02.21 | 26.02.21 | Material Not Allocated | 28.02.21 | 2
341 | Hasilpur | 15454005479 | 19.02.21 | B-1 | 19 | 23.02.21 | 2021-02-26 | Material not allocated | 2021-02-28 | 2
342 | Kahror Pacca | 15463004727 | 1/26/2021 | B-1 | 19 | 2021-01-27 | 2021-02-26 | Material not allocate | 2021-02-28 | 2
343 | Pakpattan | 961/B1 | 18/01/21 | B-1 | 19 |  | 29/01/21 | allocation awaited | 28.02.21 | 2
344 | Arifwala | 747/B-1 | 31.12.20 | B-1 | 20 | 01.01.21 | 29.01.21 | Allocation of Material Awaited | 28.02.21 | 2
345 | Muzaffargarh | 15719008100 | 17.02.2021 | B-1 | 19 |  | 26.02.2021 | Material allocation awaited | 28.02.2021 | 2
346 | Kot Addu | 15723009755 | 26.02.2021 | B-1 | 19 |  | 26.02.2021 | Material allocation awaited | 28.02.2021 | 2
347 | Kot Addu | 15724007291 | 26.02.2021 | B-1 | 19 |  | 26.02.2021 | Material allocation awaited | 28.02.2021 | 2
348 | Layyah | 15734009129 | 16.02.2021 | B-1 | 19 |  | 26.02.2021 | Material allocation awaited | 28.02.2021 | 2
349 | Alipur | 15742009303 | 17.02.2021 | B-1 | 19 |  | 26.02.2021 | Material Allocation awaited | 28.02.2021 | 2
350 | Alipur | 15743009418 | 22.01.2021 | B-1 | 19 |  | 26.02.2021 | Material Allocation awaited | 28.02.2021 | 2
351 | Chishtian | 15831007715/B1 | 2021-01-24 | B-1 | 24 | 2021-02-09 | 26.02.21 | Material demanded | 28.02.21 | 2
352 | Kabirwala | 001874 | 2020-11-19 | B-1 | 24 | 2020-11-25 | 2021-02-26 | Total Material Required | 2021-02-28 | 2
353 | Kabirwala | 003773 | 2021-02-25 | B-1 | 23 | 2021-02-26 | 2021-02-26 | Total Material Required | 2021-02-28 | 2
354 | M/Channu | 1071/B-1 | 24.02.21 | B-1 | 16 | 26.02.21 | 26.02.21 | Total Material Required | 2021-02-28 | 2
355 | Pakpattan | 964/BI | 28.01.21 | B-1 | 19 |  | 30.01.21 | allocation awaited | 28.02.21 | 1
356 | Chishtian | 15831007992/B1 | 2021-02-21 | B-1 | 20 | 2021-02-25 | 27.02.21 | Material demanded | 28.02.21 | 1
357 | Kabirwala | 002279 | 2021-02-25 | B-1 | 17 | 2021-02-26 | 2021-02-27 | Total Material Required | 2021-02-28 | 1
358 | Kabirwala | 002278 | 2021-02-25 | B-1 | 17 | 2021-02-26 | 2021-02-27 | Total Material Required | 2021-02-28 | 1
359 | Sadiqabad | 15645000862 | 19.01.2021 | B-1 | 19 | - | 28.01.2021 | Test Report Under Verification | 28.02.2021 | 0
6479.599
B-2
360 | Kabirwala | 9 | 2020-02-07 | B-2 | 35 | 2020-02-12 | 2020-05-06 | work completed at site | 2021-02-28 | 298
361 | Kabirwala | 12 | 2020-04-06 | B-2 | 68 | 2020-04-10 | 2020-05-06 | work completed at site | 2021-02-28 | 298
362 | Khanewal | 82/B-2 | 2020-03-25 | B-2 | 157 | 2020-03-31 | 2020-05-29 | work completed at site | 2021-02-28 | 275
363 | R.Y.Khan | 15613007261 | 18.07.2020 | B-2 | 38 | 22.07.2020 | 21.09.2020 | Work completed connection will be installed upto 09.03.2021 |  | 160
364 | CCW | 1301/B-2 | 13-08-20 | B-2 | 137.25 | 23-08-20 | 22-09-20 | CTs not provided by the applicant | 28.02.21 | 158
365 | Khanewal | 15912001845 | 2020-08-19 | B-2 | 300 | 2020-08-26 | 2020-09-25 | Transformer purchasing Documents is under verification | 2021-02-28 | 156
366 | Khanewal | 15916002259 | 2020-09-15 | B-2 | 37 | 2020-09-24 | 2020-09-30 | Erection of pole is under Progress | 2021-02-28 | 151
367 | Musa Pak | 13316 | 2020-10-28 | B-2 | 38 | 2020-10-29 | 2020-11-09 | Material Allocated work in Progress | 2021-02-28 | 111
368 | S.R.Alam | 15192010055/72 | 2020-10-28 | B-2 | 156 | 2020-11-04 | 2020-11-10 | Material Allocated Work in Progress | 2021-02-28 | 110
369 | Arifwala | 13-B2 | 02.11.20 | B-2 | 39.422 | 04.11.20 | 10.11.20 | Material Allocated SR Prepared | 28.02.21 | 110
370 | M/Channu | 15934001868 | 2020-10-29 | B-2 | 156 | 2020-11-05 | 2020-11-10 | Material Drawn & erection of pole is under Progress | 2021-02-28 | 110
371 | 1st Mailsi | 15351007873 | 18.11.20 | B-2 | 29 | 18.11.20 | 23.11.20 | Estimate revised due to right of way. | 28.02.21 | 96
372 | Musa Pak | 1925 | 2020-11-26 | B-2 | 38 | 2020-11-12 | 2020-11-26 | Material Allocated work in Progress | 2021-02-28 | 94
373 | HND | 15824003094 | 03.11.20 | B-2 | 499 | 13.11.2020 | 27.11.2020 | Circle Case | 28.02.22 | 93
374 | M/Channu | 15934001795 | 2020-10-21 | B-2 | 156 | 2020-11-03 | 2020-12-01 | Material Drawn & errection of pole is under Progress | 2021-02-28 | 89
375 | Rajanpur | 15244005094 | 29.12.2020 | B-2 | 68 | 02.12.20 | 29.12.2020 | -do- | 28.02.21 | 87
376 | Cantt | 15118014795 | 2020-11-06 | B-2 | 69 | 2020-11-06 | 2020-12-07 | Material Allocated Work in Progress | 2021-02-28 | 83
377 | S.R.Alam | 15191011359/27-B2 | 2020-10-16 | B-2 | 38 | 2020-11-06 | 2020-12-07 | Work Completed, M&T Awaited | 2021-02-28 | 83
378 | S.R.Alam | 03/B2/Govt | 2020-11-16 | B-2 | 38 | 2020-11-18 | 2020-12-09 | Material Allocated Work in Progress | 2021-02-28 | 81
379 | Kabirwala | 15921003111 | 2020-11-23 | B-2 | 73 | 2021-12-04 | 2020-12-11 | Material not drawn due to ERP prblem | 2021-02-28 | 79
380 | City | 15132010129/70 | 2020-10-13 | B-2 | 158 | 2020-10-16 | 2020-12-14 | Pole not Installed by Contractor | 2021-02-28 | 76
381 | S.R.Alam | 15193003560/29-B2 | 2020-11-18 | B-2 | 70 | 2020-12-01 | 2020-12-15 | Pole & rabbit Conductor not issued by Store | 2021-02-28 | 75
382 | A.P.Lamma | 15644009198 | 30.11.2020 | B-2 | 158 | - | 16.12.2020 | CTs, B/Up meter & Cable not provided by consumer | 28.02.2021 | 74
383 | G/Iqbal | 15613009235 | 13.11.2020 | B-2 | 23 | - | 21.12.2020 | CTs, B/Up meter & Cable not provided by consumer | 28.02.2021 | 70
384 | Cantt | 15118015033 | 2020-11-27 | B-2 | 69 | 2020-12-21 | 2020-12-22 | Material Allocated Work in Progress | 2021-02-28 | 68
385 | Cantt | 15118015088/75 | 2020-12-02 | B-2 | 157 | 2020-12-09 | 2020-12-22 | Material Allocated Work in Progress | 2021-02-28 | 68
386 | Arifwala | 14-B2 | 02.12.20 | B-2 | 37.79 | 07.12.20 | 24.12.20 | Material Allocated SR Prepared | 28.02.21 | 65
387 | Arifwala | 15-B2 | 02.12.20 | B-2 | 37.79 | 07.12.20 | 24.12.20 | Material Allocated SR Prepared | 28.02.21 | 65
388 | Mumtazabad | 15125008617/29 | 2020-11-23 | B-2 | 50 | 2020-12-22 | 2020-12-28 | Material Allocated Work in Progress | 2021-02-28 | 62
389 | DG Khan | 10685 | 29.12.2020 | B-2 | 38 | 02.12.20 | 30.12.2020 | Material allocated. Installation work is under process | 28.02.21 | 60
390 | Arifwala | 16-B2 | 22.12.20 | B-2 | 40.005 | 24.12.20 | 29.12.20 | Material Allocated SR Prepared | 28.02.21 | 60
391 | Shujabad | 15163010831 | 2020-12-10 | B-2 | 70 |  | 2020-12-31 | Material allocated work in Progress | 2021-02-28 | 59
392 | S.R.Alam | 15191011899/30-B2 | 2020-12-14 | B-2 | 38 | 2020-12-23 | 2020-12-31 | Pole Allocated, Balance Material Required | 2021-02-28 | 59
393 | S.R.Alam | 15191012061/31-B2 | 2020-12-29 | B-2 | 38 | 2020-12-30 | 2020-12-31 | Conductor not issued by Store | 2021-02-28 | 59
394 | Mumtazabad | 15125008723/76 | 2020-12-03 | B-2 | 350 | 2020-12-09 | 2021-01-05 | Self Purchase Documenst Awaited | 2021-02-28 | 54
395 | HND | 15825001297 | 05.12.20 | B-2 | 30 | 09.12.20 | 07.01.2021 | Partially Material recently allocated, work under progress | 28.02.21 | 52
396 | Lodhran | 415/B2 | 10.12.20 | B-2 | 19 | 14.12.20 | 2021-01-11 | Material Required | 2021-02-28 | 48
397 | Khanewal | 15913003867 | 2020-12-31 | B-2 | 37 | 2021-01-01 | 2021-01-12 | Total Material Required | 2021-02-28 | 47
398 | Mumtazabad | 15121009157/30 | 2020-12-28 | B-2 | 70 | 2021-01-11 | 2021-01-18 | Material Required | 2021-02-28 | 41
399 | Lodhran | 416/B2 | 30.12.20 | B-2 | 19 | 31.12.20 | 2021-01-18 | Material Required | 2021-02-28 | 41
400 | Zahirpir | 15624009411 | 14.12.2021 | B-2 | 69 | - | 19.01.2021 | Material allocated work under progress | 28.02.2021 | 41
401 | Kot Addu | 15722012283 | 24.12.2020 | B-2 | 38 |  | 18.01.2021 | Material allocation awaited | 28.02.2021 | 41
402 | HND | 15821003144 | 31.12.20 | B-2 | 40 | 31.12.20 | 25.01.2021 | Partially Material recently allocated, work under progress | 28.02.21 | 35
403 | Khanewal | 15913003868 | 2020-12-31 | B-2 | 65 | 2021-01-15 | 2021-01-26 | Total Material Required | 2021-02-28 | 33
404 | DG Khan | 6247 | 21.01.21 | B-2 | 38 | 22.01.21 | 26.01.21 | Rabbit Conductor Required | 28.02.21 | 32
405 | Layyah | 15731012438 | 14.12.2020 | B-2 | 38 |  | 27.01.2021 | Material allocation awaited | 28.02.2021 | 32
406 | Mumtazabad | 15125009103/31 | 2021-01-18 | B-2 | 70 | 2021-01-25 | 2021-01-29 | Material Required | 2021-02-28 | 30
407 | DG Khan | 9134 | 28.01.21 | B-2 | 25 | 29.01.21 | 29.01.21 | Rabbit Conductor Required | 28.02.21 | 30
408 | Kot Addu | 15723008548 | 02.12.2020 | B-2 | 70 |  | 29.01.2021 | Material allocation awaited | 28.02.2021 | 30
409 | Kot Addu | 15724007284 | 28.01.2021 | B-2 | 38 |  | 29.01.2021 | Material allocation awaited | 28.02.2021 | 30
410 | Lodhran | 418/B2 | 27.01.21 | B-2 | 19 | 29.01.21 | 2021-02-01 | Material Required | 2021-02-28 | 27
411 | Pakpattan | 22 | 20.11.20 | B-2 | 40 |  | 04.02.2021 | Particially material allocated | 28.02.21 | 24
412 | Kot Addu | 15722007916 | 27.02.2020 | B-2 | 78 |  | 04.02.2021 05.03.2020 | Estimate Revised, 1-HT Pole + 653-Mtrs Dog Conductor Required | 28.02.2021 | 24
413 | Cantt | 15118015762 | 2021-01-25 | B-2 | 69 | 2021-01-27 | 2021-02-08 | Material Required | 2021-02-28 | 20
414 | Cantt | 15118015763 | 2021-01-25 | B-2 | 69 | 2021-01-27 | 2021-02-08 | Material Required | 2021-02-28 | 20
415 | Kot Addu | 15721006886 | 07.01.2021 | B-2 | 70 |  | 08.02.2021 | Material Allocation Awaited | 28.02.2021 | 20
416 | Lodhran | 419/B2 | 01.02.21 | B-2 | 19 | 04.02.21 | 2021-02-09 | Material Required | 2021-02-28 | 19
417 | Mumtazabad | 15121009440/32/B2 | 28.01.21 | B-2 | 69 | 2021-02-08 | 2021-02-10 | Material Required | 2021-02-28 | 18
418 | Khanewal | 15912003483 | 2021-02-01 | B-2 | 100 | 2021-02-02 | 2021-02-12 | Total Material Required | 2021-02-28 | 16
419 | Khanewal | 15913004095 | 2021-01-27 | B-2 | 38 | 2021-02-12 | 2021-02-13 | Total Material Required | 2021-02-28 | 15
420 | S.R.Alam | 15192010616/32 | 2020-12-30 | B-2 | 38 | 2021-01-16 | 2021-02-16 | Material Required | 2021-02-28 | 12
421 | Lodhran | 420/B2 | 09.02.21 | B-2 | 19 | 10.02.21 | 2021-02-16 | Material Required | 2021-02-28 | 12
422 | Cantt | 15118015949/79 | 2021-02-09 | B-2 | 100 | 2021-02-17 | 2021-02-17 | Material Required | 2021-02-28 | 11
423 | Khanpur | 15623006967 | 28.01.2021 | B-2 | 34 | - | 17.02.2021 | Material to be drawn | 28.02.2021 | 11
424 | Mumtazabad | 15125009011/77 | 2021-01-08 | B-2 | 156 | 2021-01-22 | 2021-02-18 | SCO under Process | 2021-02-28 | 10
425 | Sahiwal-1 | 15513011504/ 1211/B-1 | 01.02.21 | B-2 | 38 | 14.02.21 | 18.02.21 | Material not allocated | 28.02.21 | 10
426 | HND | 15821003190 | 22.01.21 | B-2 | 69 | 28.01.2021 | 22.02.2021 | Material demanded | 28.02.21 | 6
427 | Musa Pak | 15195016914 | 2021-02-03 | B-2 | 38 | 2021-02-23 | 2021-02-24 | Material Required | 2021-02-28 | 4
428 | S.R.Alam | 15192011052/80 | 2021-02-10 | B-2 | 140 | 2021-02-23 | 2021-02-26 | SCO under Process | 2021-02-28 | 2
429 | Cantt | 15118017390 | 2021-02-25 | B-2 | 60 | 2021-02-26 | 2021-02-26 | Material Required | 2021-02-28 | 2
430 | DG Khan | 12639 | 23.02.21 | B-2 | 68 | 24.02.21 | 26.02.21 | Total Material is required | 28.02.21 | 2
431 | Arifwala | 17-B2 | 08.02.21 | B-2 | 39.3 | 10.02.21 | 26.02.21 | Allocation of Material Awaited | 28.02.21 | 2
432 | R.Y.Khan | 15618006443 | 28.01.2021 | B-2 | 69 | - | 28.02.2021 | Material to be drawn | 28.02.2021 | 0
5609.557
B-3
433 | CITY | 109 | 23.07.2018 | B-3 | 4890 | 24.07.2018 | 27.07.18 | RIGHT OF WAY | 28.02.21 | 893
434 | M.GARH | 110 | 23.07.2018 | B-3 | 4950 | 24.07.18 | 27.07.18 | RIGHT OF WAY | 28.02.21 | 893
435 | K.ADDU | 107 | 17.05.18 | B-3 | 1280 | REVISED | 05.06.18 | RIGHT OF WAY | 28.02.21 | 961