## 8-2019
PRIORITY LIST OF PENDING RIPE CONNECTIONS WHERE 400KVA & 630KVA TRANSFORMERS PROPOSED
IN RESPECT OF MEPCO CIRCLE SAHIWAL | [9 empty] | UPTO 31.08.2019
Name of Divn: | Name of S/Divn: | Application |  | Name of Consumer | Sanctioned Load (KW) | Tariff | Capacity of Transformer | Date of Payment | SCO / SJO |  | Reason for non-installation of connection
|  | No | Date | [5 empty] | No | Date
SWL-ll | City SWL | 425/C1/G | 08.08.17 | Superintending Jail SWL | 272-00 To 437-00 | C1G EOL | 630-KVA | 27.03.18 | - | - | T/Former not purchased by agency uptill now
SWL-l | Rural SWL | 23/A3/G | 09.01.19 | Regional Training Institute Chak No. 87/9-L Sahiwal | 319.91 | A3 | 400-KVA | 22.01.19 |  |  | T/Former not purchased by agency uptill now
SWL-l | Rural SWL | 488/B2/EOL | 03.12.18 | Shiraz Zahid PPN Chowk | 320-00 To 484-00 | B2 EOL | 630-KVA | 29.01.19 | - | - | T/Former not purchased by consumer uptill now
AW | SWL Road | 1268/B2 | 26.03.19 | Iftikhar Ahmad 207/EB | 399.228 | B2 | 630-KVA | 08.04.19 | 000046 | 30.07.19 | Work under Process
AW | SWL Road | 1273/B2 | 15.05.19 | Muhammad Usman Ali 155/EB | 319.696 | B2 | 400-KVA | 14.06.19 |  |  | Letter issued to Manager-l (QA&I) NTDC Lahore for re-verification
AW | Qaboola | 17/A1/G | 17.10.17 | THQ Hospital Arifwala | 499.99 | A1 | 630-KVA | 20.06.19 |  |  | T/Former not purchased by agency uptill now
SWL-ll | City SWL | 9/C1/G | 09.01.19 | M/S Trans Freight STA NLC SWL | 498.22 | C1/G | 630-KVA | 25.06.19 |  |  | T/Former not purchased by agency uptill now
PPN | Noor Pur | 1274/B2 | 12.06.19 | Muhammad Zahid Iqbal Pir Ghani Road Pakpattan | 319.83 | B2 | 400-KVA | 03.07.19 |  |  | Letter issued to purchase T/Former
AW | SWL Road | 1275/B2 | 24.06.19 | Mst. Razia Ishrat 147/EB | 319 | B2 | 400-KVA | 09.07.19 |  |  | Letter issued to Manager-l (QA&I) NTDC Lahore for re-verification
SWL-2 | Multan Rd | 500/B2/EOL | 05.07.19 | Chief Officer TMA SWL Disposal 86/9-L | 40.00 to 240.00 | B2 | 400-KVA | 14.06.19 |  |  | Letter issued to purchase T/Former
PPN | Power House | 506/B2/EOL | 23.07.19 | Fazal Ahmad Chak 19/SP | 160.00 to 320.00 | B2 | 400-KVA | 31.07.191 |  |  | Letter issued to Manager-l (QA&I) NTDC Lahore for re-verification
PPN | Noor Pur | 313/A2C | 01.03.19 | M/S Baqri Trading Co. Oil Depott. Chak No. 79/D | 195.76 | A2 | 400-KVA | 06.08.19 |  |  | T/Former not purchased by consumer uptill now
CCW | Ghazi Abad | 1279/B2 | 26.07.19 | Muhammad Shafiq Chak No. 176/9-L | 319.83 | B2 | 400-KVA | 09.08.19 |  |  | Test Report under verification
| No. _________________________ | [7 empty] | Date ___________________
Copy is forwarded to Chief Execfutive Officer [Attn: Addl: CS Director] MEPCO Ltd: Multan for inforamtion please
Superintending Engineer (OP),
MEPCO Circle Sahiwal