## Phase-I
DEVELOPMENT WORKS REGARDING PRIME MINISTER'S GLOBAL SDGs PROGRAMME IN RESPECT OF DISCOS.
Name of Company: MEPCO |  |  | Phase-I | District Bahawalnagar |  | Status Ending Date: 08-12-2017
Sr. No. | Name of Scheme | Tehsil | District | Financial Progress (Fund utilized) | Physical Progress | Material available | Planned Date of completion Schemes | Actual Date of Completion
1 | Bhani Muhammad Aslam Mouza Malay Shah | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
2 | A.A M Aslam Sukhera Ward No 7 Mohallah Nizam Pura Mouza Mandi Sadiq Ganj | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
3 | Basti Noor Ky Haji M Yar Shaikho Ka Mouza Mali Sheikho Ka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
4 | Basti Malikani Mouza Bilara Mahamnd Baloch | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
5 | Basti Hafiz Abdul Waheed Dhudhi & Mai Kejan Wali Mouza Lalo Kakla | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
6 | Bhani Azhar Hussain Jodheka Mouza Bachiyan Wali | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
7 | Bhani Muhammad Ali, Shahzad Mouza Bachiyan Wali | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
8 | Azafi Basti Bachiyan Wali Mouza Bachiyan Wali | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
9 | Basti Khokhran Wali & Yaseen Mouza Laleka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
10 | Basti Muhammad Shafi Arrian Mouza Laleka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
11 | Basti Sikander Wiseldera Mouza Laleka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
12 | Basti Ch;Muhammad Sadique Arrian Mouza Bhindi Laleka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
13 | Basti Shabir Main & Ch Maqsood Mouza Gajjan Dhudhi | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
14 | Basti Ahmad Din Banwara Mouza Toba Balochan | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
15 | Basti Darbar Baghwan Mouza Ramzan Langah | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 08-2017 | 08-2017
16 | Basti Zafar Mochi Mouza Toba Qalander Shah | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
17 | Basti Noor Ahmad Joyia Mouza Makhna Rajeka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
18 | Basti Baghar Wala Khoo Mouza Makhna Rajeka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
19 | Basti Ghuni Pur of Ghani Pur | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
20 | Abadi Darbar Wali of Ghani Pur | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
21 | Basti Admir Wali of Akuka Hittar | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
22 | Ext Of LT Line Saleem Shah & Basti Shahid Qaim Ka Mouza Kalia Shah | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
23 | Basti Abdul Razzaq Mouza Sadiq Nagar | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
24 | Basti Bashir Ahmed Mouza Sadiq Nagar | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
25 | Basti Dhegan Pura of Bair Wala | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
26 | Basti Muhamamd Akram, Roshan Din Mouza Fidai Shah | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
27 | Azafi Abadi School Wali,Lateef Sunara Mouza Fidai Shah | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
28 | Bhani Naseera Nonari Mouza Fidai Shah | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
29 | Basti Jahangir Behram Ka Mouza Fidai Shah | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
30 | Basti Arif Shah Mouza Chakooka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
31 | Basti Anwar Chakooka Acha Nagar Mouza Chakooka | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
32 | Basti Farooq Khan Baloch Mouza Bonga Balochan | MND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
33 | Basti Shabbir Wali Mouza Rabnawaz Pura | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 05-2017 | 05-2017
34 | Basti Amin Kot Mouza Billoka | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
35 | Basti Rafique Jutt Mouza M.Nawaz Pura | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 05-2017 | 05-2017
36 | Basti Shahrah Lakhan Mouza Hafiz Wala | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
37 | Basti Ali Muhammad Bodla Mouza Islam Pura | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
38 | Basti Tibba Noor Shah Mouza Islam Pura | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
39 | Provision of Electricity in Basti Sarwar Abad Mouza Islam Pura | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
40 | Provision of Electricity in Basti Holan Wali Mouza Fateh Pur Holan | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
41 | Rehablitation of Chak Faqeer Shah,Farzand Ali Joiya Mouza Faqeer Shah | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
42 | Basti Haji Muhamamd Ismail Mouza Kacha Qazi Wala | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
43 | Basti Haji Haneef Numberdar Mouza Kacha Qazi Wala | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
44 | Provision of Electricity in Basti Pull Rajay Wali Mouza Kat Sher Muhammad | BWN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
45 | Provision of Electricity in Basti Ghulam Farid Akuka & M.Ali Akuka Mouza Dulla Akuka | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
46 | Provision of Electricity in Basti Bashir Mahia Mouza Mahta Jhedu | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 05-2017 | 05-2017
47 | Basti Jahangir Khoker Mouza Qabool Fitani | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
48 | Basti Gul Pura Talib Joiya Mouza Mahar Sharif | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 06-2017 | 06-2017
49 | Basti Abdul Rehman Jalooka & Khattay Wala Khoo Mouza Mahar Sharif | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 05-2017 | 05-2017
50 | Provision of Electricity in Basti Chah Hafiz Wala Khoo Mouza Mahar Sharif | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
51 | Basti Jan Muhammad Lakhwera, Sharif Sanaya & Riaz Jhedu Mouza Jewan Lakhwera | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 08-2017 | 08-2017
52 | Basti Afzal Joiya & Jalal Jhedu Mouza Chak 02/FW | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 05-2017 | 05-2017
53 | Basti Hatam Mouza Bonga Jhedu | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
54 | Basti Allah Yar Joiya Mouza Bonga Jhedu | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
55 | Basti Naian Wali Mouza Kameera | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
56 | Basti Ahmad Shah Mouza Rajo Shah | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 08-2017 | 08-2017
57 | Basti Lal Khan Mouza Mahar Shareef | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
58 | Basti Moazam Ali Kichi Mouza Mahta Jhedu | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
59 | Basti Haji Ali Mohammad, Nawaz Lakhwera of Meeru Balouch | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
60 | Basti Jalal Khan Bhadera of Meeru Balouch | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
61 | Basti Chah Bamoo Khan Bhadera of Meeru Balouch | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
62 | Basti Sher Khan Dad Potra of Azeem | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
63 | Basti Allah Ditta Numberdar of Azeem | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
64 | Provision of Electricity to Basti Ghulam Muhammad Bhadera of Azeem | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
65 | Basti Nazam Jhedu of Shaher Farid | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
66 | Basti Akbar Ali,Nisar Goru Chak No. 93/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
67 | Provision of Electricity to Basti Master Akram Bhadera,M.Yar Arrain of Shaher Farid | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 08-2017 | 08-2017
68 | Basti Ghulam Fareed Chishti, Shah M.May of Shaher Farid | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 08-2017 | 08-2017
69 | Provision of Electricity to Basti Alawal Sabhaji of Thingi Balouchan | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
70 | Basti Hakim Ali Bhadera of Lunda | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
71 | Basti Muhammad Amin Arrian of Lunda | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
72 | Provision of Electricity to Basti Roshan Din Rehmani of Soda | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
73 | Provision of Electricity to Basti Baba Zakrya Rajpoot of Soda | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
74 | Provision of Electricity to Basti Yasin Jossar Wali of Soda | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
75 | Provision of Electricity to Reh of Azafi Abadi Fareed kot, Khuda Bux of Soda | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
76 | Provision of Electricity to Reh: of Basti Qalendar Shah of Soda | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
77 | Basti Mohammad Riaz Joiya (Sharqi) of Badana Sharqi | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
78 | Basti Shams Din Joiya,Amin Chishti of Badana Sharqi | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
79 | Basti Haji Ramzan Jhunjh, Allah Bux Arrian, Aslam Rehmani of Mubarik Pur | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 08-2017 | 08-2017
80 | Provision of Electricity to Basti Irshad Jutt of Qabool Fatani | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 06-2017 | 06-2017
81 | Elect/Ren of Azafi Abadi Qabristan Wali | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
82 | Provision of Electricity to Reh: of Basti Balouchan Wali | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 06-2017 | 06-2017
83 | Reh: of Chak No.07/FW, Arif Junjh | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
84 | Provision of Electricity to Azafi Abadi Chak No.95/F Nai Wala | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 05-2017 | 05-2017
85 | Provision of Electricity to Elec: Ren Basti Chak No.95/F School Wala, Ch. Abdul Rehman | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 05-2017 | 05-2017
86 | Provision of Electricity to Basti Darbar Wali Chak No.212/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 04-2017 | 04-2017
87 | Provision of Electricity to Basti Azmat Khan Niazi of Chak No.94/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
88 | Provision of Electricity to Basti Ameer Khan, Wazeer Khan Niazi of Chak No.94/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
89 | Provision of Electricity to Azafi Abadi Chak No. 210/F, Liaqat Boota | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
90 | Provision of Electricity to Basti Asad Ali Khan Chairman of Chak No.08/FW | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
91 | Provision of Electricity to Reh: of Chak No.09/FW Mohammad Saleem, Mohammad Shafi | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 04-2017 | 04-2017
92 | Basti Dr. Abdul Ghafar Baloch of Jaman Shah | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
93 | Reh Basti Khaliq Maral Chak No. 45/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
94 | Provision of Electricity to Reh: of Chak No.56/F School Wali, Akram Wali | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
95 | Provision of Electricity to Basti Aslam Niazi Chak No.53/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
96 | Rehabilitation of Electricity to Chak No.107/F, Mushtaq Shah Tehsil Chishtian | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
97 | Elec: Renovation of Basti Khichian Wali Chak No.45/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
98 | Reh: of Azafi Basti Chak No.97/F, Nawaz | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
99 | Azafi Abadi Chak No.440/6-R, Zafar Pedhiar Wali | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
100 | Provision of Electricity to A.A.Chak No. 37/3-R Farooq Azam Wali, | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
101 | Provision of Electricity to Reh: of A.A.Chak 33/3-R, Dilawar Jajja, Near Solangi Marriage Hall | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
102 | Provision of Electricity to Reh of Chak No. 53/F Ashiq Niazi | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
103 | Provision of Electricity to Basti Abdul Sattar Joiya Chak No.170/M | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 10-2017 | 10-2017
104 | Provision of Electricity to Elec: Renovation of Ada Chak No.177/M, M. Amin, Arshad Gujjar | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
105 | Provision of Electricity to Reh: of Basti Taj Pura Chak No.97/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
106 | Provision of Electricity to Elec: Ren of Basti Imam Shah, Basti Asghar Ali Arrian, Chak No.99/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
107 | Provision of Electricity to Elec: Renovation of Chak No.100/F, Shouqat Mughal | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
108 | Provision of Electricity to Reh: of Chak No.98/F, Beequ Khan | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
109 | Provision of Electricity to Elec: / Renovation Chak No.106/F Aqeel Gill & Shabbir Butter | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
110 | Provision of Electricity to Basti Rana Akram Chak No.102/F | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
111 | Provision of Electricity to Basti Tasadak Cheema, Akbar Ali Guru Chak No.174/M | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 06-2017 | 06-2017
112 | Basti Rana Bashir Ahmad Chak No.441/6-R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
113 | Reh: of Azafi Abadi Chak No.435/6-R Anwar Wali | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
114 | Basti Iftikhar Ahmad Jutt Chak No. 438/6-R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
115 | Provision of Electricity to Basti Sheikhan Wali Chak No. 437/6-R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
116 | Provision of Electricity to Basti Ashraf Nadeem Balouch Chak No. 11/FW | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
117 | Provision of Electricity to Basti Ehsaan Jutt Chak No. 437/6-R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
118 | Provision of Electricity to Reh: of Basti Sarwar Shaikh Chak No.429/6-R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
119 | Provision of Electricity to Reh: Chak No. 131/6-R, Garbi, Khadim Hussain Jutt | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
120 | Provision of Electricity to Azafi Basti Chak No. 02/1-R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 06-2017 | 06-2017
121 | Provision of Electricity to Reh: of Chak No. 50/F, Malik Irshad,vAshraf,vIjaz, Allah Yar | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 05-2017 | 05-2017
122 | Provision of Electricity to Reh: of Azafi Abadi 129/M, Faizan Wali | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
123 | Basti Ch. Saeed Ahmed Jutt Chak No.428/6-R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 06-2017 | 06-2017
124 | Reh: of Chak No.60/4-R, Waseem Murtaza | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
125 | Reh: of Chak No.108/6-R Sajjid, Razzaq Arrian | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
126 | Reh of Chak No. 74/4-R, M. Akram | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 06-2017 | 06-2017
127 | Reh of Azafi Basti Chak No. 48/F, Siddiq Kamboo Wali | CTN | B/Nagar | 100% | 100% | All Procured Material Installed | 08-2017 | 08-2017
128 | Basti Tayyub Wali Chak 49/3-R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 06-2017 | 06-2017
129 | Extension of LT Chak No. 74/4-R & Dera Shah Muhammad | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
130 | Rehabilitation of Azafi Abadi Chak No. 84/5R | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
131 | Abadi Chak No. 121/6R Talib Abad | HND | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
132 | Basti Wali Ullah (Muhammad) Chak No. 340/HR | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
133 | Azafi Basti Balochan Wali Chak No. 197/HB | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
134 | Azafi Basti Chak No. 209/9-R | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
135 | Azafi Basti Chak No. 204/9-R Moor | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
136 | Azafi Basti Chak No. 205/9-R (Darbar Wali) | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 09-2017 | 09-2017
137 | Azafi Basti Mian Naseer Dhudhi Chak No. 265/HR | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
138 | Reh: Azafi Abadi Lateef Wali Chak No. 274/HR | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
139 | Azafi Basti Chak No. 208/9-R Bara | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 07-2017 | 07-2017
140 | Azafi Basti Baba Abdul Sattar Wali Chak No. 239/HB | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
141 | Azafi Basti Muhammad Hanif Wali Chak No.235/9-R | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
142 | Chah Tarkhan Wala Mouza Chappan Badry Das | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
143 | A.A.Rattan Pura Mouza Rattan Pura | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
144 | Taj Wala Khoo Mouza Poggal | MND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
145 | Basti Abdal Joyia, Usman Ghani Jummo etc. Mouza Mansoor Dewa | MND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
146 | Basti Mushtaq Ahmad Mughal Khod Mouza Rohana | MND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
147 | Azafi Abadi Sukha Nand Mouza Sukha Nanad | MND | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
148 | Basti Muhammad Ashraf Mouza Sukha Nanad | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
149 | Bhani Tanveer Qaim Khani Mouza Harran Wala | MND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
150 | Basti Muhammad Ashraf Mahar & Azafi Abadi Mouza Tabqaray | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
151 | Bhani Mian Niaz Ahmad Mouza Mirzeka | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
152 | Bhani Shera Kharal Mouza Musla Allah Yar | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
153 | Basti Pir Ali Ahmad & Bashir Ahmed Chishti Mouza Kakwani | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
154 | Basti Kaly Wali Mouza Shamas Wala | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
155 | Basti Bakhshaya Mouza Shamams Wala | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
156 | Basti Sanateka Mouza Shamas Wala | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
157 | Nai Abadi Shah Karam Mouza Shah Karam | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
158 | Basti Chah Kaly Khan Mouza Karam Pur Gadhoka | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
159 | Basti Haji Saeed Ahmad Rateka Mouza Ratteka Ottar | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
160 | Basti Muhammad Sharif Mouza Sharaf Shah | MND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
161 | Basti Sukherian Wali Mouza Murad Wala | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
162 | Nai Abadi Wazir Ka & Basti Ahmed Yar Mouza Wazir Ka | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
163 | Basti Lakhoka Mouza Momeka | MND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
164 | Basti Said Jalal Mouza Qasim Ka | MND | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
165 | Basti Hamid Choharka Mouza Akuka Hittar | MND | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
166 | Basti Mian Afzal Chakooka Mouza Bonga Akber | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
167 | Basti Maqsood Chakooka Mouza Mari Chakooka | MND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
168 | Basti Fazil Wali of Ali Goher | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
169 | Azafi Abadi Said Ali & Khan Muhamamd Mouza Said Ali | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
170 | Azafi Abadi Masjid Murad Shah,Iqbal Kalas Mouza Said Ali | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
171 | Azafi Abadi Mall Shah Mouza Mosam Wala | MND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
172 | Basti Muhammad Hussain Punn & LT Extension Punnan Wali | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
173 | Basti Muhammad Amin Baloch & Abdullah Baloch Mouza Ismail Pur Balochan | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
174 | Basti Hari Pura Mouza Hari Pura | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
175 | Basti Zulfiqar Dhudhi Mouza Akuka Hittar | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
176 | Basti Ghulam Farid Mouza Akuka Hittar | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
177 | Basti Sattar Wali Mouza Noor Muhammad Bhangran | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
178 | Basti Muhamamd Hussain & Raika Wali Mouza Sadiq Nagar | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
179 | Basti Muhammad Yar Mouza Mari Qadir Bux | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
180 | Basti Hansan Wali Mouza Mari Qadir Bux | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
181 | Basti Noor Samand of Momeka | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
182 | Basti Bashir Momeka Mouza Momeka | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
183 | Basti Allah Yar & LT Extension Asif Ranooka Mouza Khillo Wala | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
184 | Basti Ghulam Muhammad Jodhiyana Mouza Jodheka | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
185 | Basti Noor Muhamamd Hamandka Mouza Billoka | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
186 | Basti Allah Jawaya Mouza Qamar Din Bodla | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
187 | Basti Chah Bootay Wala Mouza Bonga Machi | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
188 | Basti Adil Ahloka Mouza Mahar Khurd | MND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
189 | Basti Memora Dhudhi Mouza Kabootri | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
190 | Basti Shahbaz Main Mouza Attar Singh Sani | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
191 | Basti Rohana of Attar Singh Sani | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
192 | Basti Khan Muhamamd Mouza Attar Singh Sani | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
193 | Basti Manzoor Kharal Mouza Jall Wala | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
194 | Basti Saddique Kanera | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
195 | Basti M. Ali Khokher & Rehablitation of Wazir Wali | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
196 | Basti Muhamamd Ali, Allah Bux Bhatti, LT Extension of Liaqat Shah Mouza Garnaj | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
197 | Basti Mai Zulekha | MND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
198 | Basti Pir Ishaq Chishti Mouza Gulab Ali | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
199 | Provision of Electricity in Basti Mushtaq Joiya & Iqbal Khan Mouza Khiraj Pura | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
200 | Basti Manzoor,Anwer & LT Ext of Labh Singh Mouza Labh Singh | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
201 | Basti Muhammad Khan Langay Ka Kishan Garh | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
202 | Basti Ishaq Joiya Mouza Qaiser Singh | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
203 | Basti Said Muhamamd Langay ka & M.Hanif Mouza Chak Ghulam Muhamamd | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
204 | Basti Kot Ahmed Yar &Jam Imran & Lt Extension of Riaz Abad Mouza Chak Ghulam Muhamamd | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
205 | Basti Qasim Ali Sukhera Mouza Akan Wali | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
206 | Basti Asghar Kamboh & M.Din Joiya Mouza Sardar Shah | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
207 | Provision of Electricity in Basti Kareem Bux Mamoonka Mouza Dadu Mamoonka | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
208 | Provision of Electricity in Basti Noor Pura Mouza Moran Wala | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
209 | Provision of Electricity in Basti Wazeer Abad Mouza Kot Himraj | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
210 | Provision of Electricity in Basti Sultan Mehmood Gopayra & Madad Ali Mouza Bajak | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
211 | Provision of Electricity in Basti Sukherian Wali Mouza Toba Rehman Shah | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
212 | Provision of Electricity in Basti Haji Allah Din Dhudhi Mouza Dinan Bashnoian | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
213 | Provision of Electricity in Basti Muhammad Diwan Mouza Bhorji | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
214 | Provision of Electricity in Basti Ghazi Khelana Mouza Dinan Bashnoian | BWN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
215 | Basti Shaffi Khan Jamlera Mouza Dulla Akuka | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
216 | Provision of Electricity in Basti Ch Shabbir Arrian Mouza Qabool Fitani | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
217 | Basti Ghulam Hassan Baig Mouza Qabool Fatani | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
218 | Basti Ali Garh Mouza Mari Shoke Elahi | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
219 | Basti Ameen Khan Bhadera, Naseer Balouch of Azeem | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
220 | Basti Abdullah Kharal Wali, Munir Ahmad Kulera of Sheli Gharbi | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
221 | Basti Falak Sher Khokhar of Sheli Gharbi | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
222 | Provision of Electricity to Reh of Basti Buxan Khan of Chak No.08/FW | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
223 | Provision of Electricity to Reh of Chak No.08/FW Pervaiz Akber | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
224 | Provision of Electricity to Basti Tibbi Rathia, Exten LT Line Basti Rathia | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
225 | Reh: of Chak No.05/FW, Basti Ahmad Din Joiya, Nizam Din Arrian | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
226 | Provision of Electricity to Reh: of Chak No.06/FW Iqbal Kulera | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
227 | Provision of Electricity to Reh: of Chak No.07/FW Rawan Wala | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
228 | Provision of Electricity to Reh: of Chak No.07/FW Tahir Wala | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
229 | Provision of Electricity to Reh of Chak No. 55/F Rana Zafar | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
230 | Reh: of Basti Rashid Kamboo Wali Chak NO.48/F | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
231 | Reh: of Basti Malik Ali Mohammad Chak No.96/F | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
232 | Provision of Electricity to Basti Master Irshad, Gulam Rasool Bajwa, Safdar Chak NO.37/3-R | HND | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
233 | Provision of Electricity to Basti Javed Gujjar Wali Chak No.98/F | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
234 | Provision of Electricity to Azafi Basti Chak No.98/F Tahir Hussain Gujjar | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
235 | Provision of Electricity to Elec: Ren of Basti Hassan Ali Arrian of Chak No.99/F | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
236 | Provision of Electricity to Azafi Basti Chak No.106/F Irshad Gill | CTN | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
237 | Elec: Renovation Chak No.430/6-R, Arshad Sultan,Zafar Iqbal Cheema | HND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
238 | Provision of Electricity to Reh: of Chak No.434/6-R Karamat Gill, Bashir Balouch, Saif Chattah | HND | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
239 | Rehabilitation Ghousia Colony Faqir Wali | HND | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
240 | Rehabilitation Chak No. 86/5-R Beri Wala Basti | HND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
241 | Chak 102/6-R Dera Baba Allah Rakha | HND | B/Nagar | 90% | 90% | Transformer under procurement | 08-2017 | Ending 12-2017
242 | Azafi Abadi Chak No. 164/7-R | HND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
243 | Rehabilitation Chak No. 75/4R | HND | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
244 | Chak No. 159/7-R and extension of LT Chak No.159/7-R | HND | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
245 | Basti Bangla Colony Babu Mistry Chak 272/HR | F/Abbas | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
246 | Ikhlaq (M. Shafique Basti) Near Water Supply Chak No. 274/HR | F/Abbas | B/Nagar | 90% | 90% | Transformer under procurement | 09-2017 | Ending 12-2017
247 | Provision of Electricity in Azafi Basti Sultan Wali Chak No. 301/HR | F/Abbas | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
248 | Azafi Basti Baba Lal Wali Chak No. 232/9-R | F/Abbas | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
249 | Azafi Basti Jinnah Colony Chak No. 237/9-R | F/Abbas | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
250 | Azafi Basti Rafique Panwar Mouza Chak No. 337/HR | F/Abbas | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
251 | Azafi Basti Chak No. 224/9-R Mouza Chak 224/9-R | F/Abbas | B/Nagar | 90% | 90% | Transformer under procurement | 10-2017 | Ending 12-2017
252 | Azfi Basti Liaquat Abad Mouza Chak No. 199/7-R | F/Abbas | B/Nagar | 90% | 90% | Transformer under procurement | 11-2017 | Ending 12-2017
253 | Basti Haji Muhammad Akbar Kharal Mouza Jhari Wala | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
254 | Basti Shah Muhammad Mouza Rasool Pur | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
255 | A.A.Chak Darbari Janubi Side Darbari | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
256 | Azafi Abadi Kahin Singh Kharkan Mouza Kahan Singh Khurkan | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
257 | Provision of Electricity in Abadi Kaidar Pur Mobeen Baloch Mouza Kaidar Pur | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
258 | Azafi Abadi Habib Ka Gharbi Mouza Habib Ka | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
259 | Basti Joyian Wali Mouza Kot Makhdoom | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
260 | Basti Chak Tehsildar Mouza Chaveka Ottar | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
261 | Bhani Noor Ahmad Bhoreka,Irshad &Arrian wali Mouza Pir Shah | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
262 | Azafi Basti Kameera Mouza Kameera | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
263 | Basti Khan Muhammad,Jalal Kot Mouza Syed Wala | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
264 | Basti Maham Ali Wali Mouza Mosam Wala | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
265 | Azafi Abadi Chabiana & LT Extension Mouza Ghabond Pur | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
266 | Basti Ashraf Watoo Mouza Fareed Abad | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
267 | Basti Abdul Ghafoor Dhudhi | MND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
268 | Basti Bagh Wala & Noor Din Mouza Bhamoo Wala | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
269 | Shareef Bhoreka Mouza Bhoureka | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
270 | Basti Allah Ditta Kharadiya Mouza Attar Singh Sani | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
271 | Basti Younis & Arrian Wala Mouza Samand Singh | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
272 | Basti Tiba Iqbal Jhurrar & Malik Mehmood Mouza Lakhmeer Dhudhi | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
273 | Basti Muhammad Saddique Mouza Mehmooda Jodheka | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
274 | Azafi Abadi Mani Sabooka Mouza Mani Sabooka | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
275 | Basti Bilal Khan Dhudhi Mouza Korian Wali | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
276 | Basti Hamid Mekan Mouza M.Nawaz Pura | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
277 | Basti Ghualam Farid Mouza Rum Wali | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
278 | Basti Haji Shamas Mouza Noor Jahanian | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
279 | Basti Allah Ditta Joiya,Allah Yar Goma Mouza Rajo Wala | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
280 | Provision of Electricity in Basti Shah Muhammad,Manzoor Ahmed Mouza Rajo Wala | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
281 | Basti Nawab Khan & LT Ext Of Basti Ghareeb Abad Mouza Labh Singh | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
282 | Basti Saeed Akhter & Sakhi Muhamamd Joiya Mouza Ratti Ram | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
283 | Basti Haji Asghar & Azafi Abadi Mouza Nai Wala | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
284 | Rehablitation of Mohallah Joiyan Wala Mouza Jand Wala | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
285 | Basti Muhamamd Nawaz Bhatti Mouza Peera Maitla | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
286 | Basti Muhammad Bux Jodhyana Mouza Naseera Jodheka | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
287 | Basti Muhamamd Munir Mouza Nathu Dhaka | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
288 | Provision of Electricity in Basti Sindhu Nagar Mouza Kot Himraj | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
289 | Provision of Electricity in Basti Ahmed Din Kulera & Joiyan Wali Moyuza Mumraj Pura | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
290 | Provision of Electricity in Basti Larran Wali Mouza Chak Abdullah | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
291 | Provision of Electricity in Basti Dildar Nagar Mouza Hazoor Singh | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
292 | Provision of Electricity in Basti Niaz Ahmed Joiya & Basti Kokara Mouza Donga Akuka | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
293 | Provision of Electricity in Azafi Abadi Ghomana Mouza Talia | BWN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
294 | Basti Saeed Khan Akuka & Dulla Ajeera Mouza Dulla Akuka | CTN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
295 | Basti Usman Akuka & Noor Samand Khan Mouza Dulla Akuka | CTN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
296 | Basti Ameer Hamza Joiya Mouza Chak 12/G | CTN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
297 | Basti Aftab Gujjar, Basti Thull Wali Chak No.99/F | CTN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
298 | Reh of A.A. Baidana Sharqi, of Badana Sharqi | CTN | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
299 | Provision of Electricity to Basti Baba Roshan Sanbhal, Bashir Ahmed,Sarfraz, Chak NO.39/3-R | HND | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
300 | Basti Hafiz Mustfa Wali Mouza Chak No. 235/9-R | F/Abbas | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
301 | Basti Yaseen Mouza Chak No. 236/9-R | F/Abbas | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
302 | Basti Qasim Wali Mouza Chak No. 236/9-R | F/Abbas | B/Nagar | 80% | 60% | HT/LT Line Material available | 25-11-2017 | Ending 12-2017
303 | Basti Yaseen Joiya | BWN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
304 | Basti Muhammad Rafiq Joiya Mouza Peera Maitla | BWN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
305 | Basti Irshad Pathan Wali Mouza Donga Bishnoian | BWN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
306 | Provision of Electricity in Basti Jahangir Khan Qasim Ka Mouza Murad Kharal | BWN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
307 | Provision of Electricity in Basti Muhammad Rafique Mouza Tukra No 1 | BWN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
308 | Provision of Electricity in Basti Irshad LT Extension Of Iqbal & Gilasian Wali Mouza Labh Singh | BWN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
309 | Basti Fareed Kot Mouza Kamal Muhammad Chishti | BWN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
310 | Basti Shah Behram of Sheli Gharbi | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
311 | Basti Peer Mohammad Shah, Sultan Kot of Sheli Gharbi | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
312 | Provision of Electricity to Basti M.Bux Rehmani, Basti Mukhtiar Wali of Chak No.08/FW | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
313 | Rehabilitation of Electricity in Chak No. 45/F Rehan Afzal Tehsil Chishtian | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
314 | Provision of Electricity to Basti Ismail Jutt Wali Chak No.441/6-R | HND | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
315 | Provision of Electricity to Reh of Chak No.174/M, Riasat Ali | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
316 | Provision of Electricity to Reh of Chak No. 169 / M, Near Thana Morr | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
317 | Provision of Electricity to Reh of Chak No.169/M Gharbi | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
318 | Provision of Electricity to Basti Abdullah Wali Chak No.169/M, Near Gulabka Factory | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
319 | Provision of Electricity to Reh / Aug of Chak No.74/4-R Malik Farooq Awan | HND | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
320 | Basti Shamoran Wali of Shahr Fareed Tehsil Chishtian | CTN | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
321 | Azafi Abadi Chak No. 150/2-L | HND | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
322 | Azafi Abadi Chak No. 85/5R | HND | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
323 | Muhallah Ghulam Rasool Chak No. 272/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
324 | Azafi Basti Jinnah Abadi Chak No.285/HR Fortabbas | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
325 | Azafi Basti Aftab Wali Chak No. 260/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
326 | Azafi Basti Tanki Wala Mouza Chak No. 328/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
327 | Azafi Basti Muhammad Sadeeq Sammah Mouza Chak No. 332/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
328 | Azafi Basti Rajran Wali Mouza Chakn No. 294/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
329 | Azafi Basti Chak No. 278/HR Gharbi | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
330 | Azafi Basti Muhammad Mansha etc Mouza Chak No. 255/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
331 | Azafi Basti Riaz Kassar Wali Mouza Chak No. 272/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
332 | Azafi Basti Kashif Wali Mouza Chak No. 319/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
333 | Azafi Basti Badana Mouza Chak No. 264/HR | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
334 | Azafi Basti Chak No. 207/9-R & EXT: Of LT Line Basti Malkan Wala Moor Mouza Chak No. 207/9-R | F/Abbas | B/Nagar | 60% | 35% | HT/LT Line Material available | Ending 11-2017 | Ending 12-2017
335 | Basti Mianwali ,Nahar Wali Mouza Khair Shah Ottar | MND | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
336 | Basti Allah Ditta Kharal | BWN | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
337 | Reh: of Azafi Abadi Meeru Balouch, Akram,Shah Muhammad of Meeru Balouch | CTN | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
338 | Basti Falak Sher, Ghaffoor Arrian of Azeem | CTN | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
339 | Provision of Electricity to Basti Bashir Ahmed Arain Chak No.204/M Tehsil Chishtian | CTN | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
340 | Provision of Electricity to Basti Bhattian Wali of Mubarik Pur | CTN | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
341 | Azafi Basti Sheikhan Wali Mouza Chak No. 311/HR | F/Abbas | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
342 | Azafi Basti Saywan Wali Mouza Chak No. 271/HR | F/Abbas | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
343 | Azafi Basti Noor Pura Mouza Chak No. 294/HR | F/Abbas | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
344 | Azafi Basti Chiristian Colony Mouza Chak No. 322/HR | F/Abbas | B/Nagar | 40% | 20% | Partial Material received remaining under procurement | Ending 12-2017 | Ending 12-2017
345 | Basti Zulfiqar | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
346 | Basti Hamid Khan | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
347 | Basti Abdul Hameed Khakwani | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
348 | Basti Peer Zaman Chishti | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
349 | Basti Khushi Arrian | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
350 | Basti Ahmed Ali Khral | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
351 | Basti Muhammad Ashrif | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
352 | Basti Allah Dita Mandel | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
353 | Basti Kharlan Wali | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
354 | Basti Noor Muhammad Arrian & EXT: Ch. Afzal | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
355 | Basti Talib Hussain Khral | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
356 | Basti Amir Ghous | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
357 | Basti Allah Rakha Janedeka | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
358 | Basti Kharlan Wali | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
359 | Basti Saleem Kot, Lt EXT: Rashid Shah And Kalia Shah | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
360 | Basti Maqbool Khokhar | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
361 | Basti Ch. Punn | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
362 | Basti Nasrullah Khokhar | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
363 | Basti Farooq Pawali | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
364 | Basti Falak Sher | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
365 | Basti Ahmad cheena | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
366 | Basti Khorsheed Cheena | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
367 | Basti Khadim Hussain | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
368 | Basti Ghulam Murtza | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
369 | Basti Muhammad Khan Watto | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
370 | Basti Mian Asjad Sarhoo | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
371 | Basti Azafi Abadi Fatoi Mehran | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
372 | Basti Takia Bagh Ali | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
373 | Basti Maqbool Jodhiyana | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
374 | Basti Rehman Pura | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
375 | Basti Shery Ka Khoo Wali Mouza Laleka | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
376 | Basti Hanif Adlana Mouza Adlana Dhudhi | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
377 | Basti Nooran Ahloka Mouza Nooran Ahloka | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
378 | Basti Darya Wala Mouza Suraj Pura | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
379 | Basti Darzian Wala Khoo Mouza Suraj Pura | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
380 | Basti Nazeer Ahloka Mouza Nooran Ahloka | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
381 | Basti Dr. Azhar Mouza Syed Wala | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
382 | Basti Yaqoob Mouza Jhulan Arrain | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
383 | Basti Shabir Shah Mouza Akuka Hittar | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
384 | Basti Rukan Din Mouza Jhulan Arrain | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
385 | Basti Abdul Razzaq Momeka | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
386 | Basti Mumtaz Dhudhi | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
387 | Basti Hanif Langah | MND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
388 | Azafi Abadi Chak No 35 & 36 Fateh Mouza 35/F | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
389 | Basti Warryam Joyia | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
390 | Basti Subha Sadiq Khokhar | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
391 | Azafi Abadi Mahni Sabuka | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
392 | Basti Bilal Kot | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
393 | Azafi Basti Balouchan | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
394 | Basti Chak Kasrayaini | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
395 | Basti Khaliqabad | BWN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
396 | Reh: of Azafi Basti Chak No.29/G Sajjad Ahmad Jatol | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
397 | Basti Mumtaz Lakhwera of Meeru Balouch | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
398 | Reh: of Basti Sheli Garbi of Sheli Gharbi | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
399 | Basti Shaher Khan Waqas Kot Wali of Sheli Gharbi | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
400 | Basti Tibbi Malkan Wali (Rahim Bux) of Sheli Gharbi | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
401 | Basti Ch. Ulfat Rasool, Khair Mohammad,Mohammad Ali of Azeem | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
402 | Basti Khadam Chokidar Wali of Sheli Gharbi | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
403 | Basti Hafeez + Jaffar Joiya of Sheli Gharbi | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
404 | Reh: of Chak No. & Azafi Abadi Chak No.133/M | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
405 | Basti Ghulam Rasool Khand,Ext. LT Basti Mukhtiar Khand of Bonga | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
406 | Basti Darbar Hubby Shah Chak No.10/FW | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
407 | Basti Mohammad Ishaq Pawli Chak No.10/FW | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
408 | Basti M. Aslam Bhatti Chak No.11/FW | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
409 | Basti Manzoor Ahmed Paloota Chak No.11/FW | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
410 | Provision of Electricity to Chak No. 136/M, Abdul Bari Tehsil Chishtian | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
411 | Provision of Electricity to Basti Fareed Khan Lakhwera of Shaher Farid | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
412 | Provision of Electricity to Elec: Ren of Basti Awana Wali,Ahmad Abad,Rafiq Rehmani of Chak No.04/FW | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
413 | Provision of Electricity to Reh: of Azafi Basti School Wali Chak No.140/M | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
414 | Provision of Electricity to Azafi Abadi Chak No.141/M | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
415 | Provision of Electricity to Elec: Renovation Basti Mohammad Yaqoob Panwar Wali Chak No.170/M | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
416 | Provision of Electricity to Basti Qasim Sheikh Wali Chak No.141/M Tehsil Chishtian | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
417 | Provision of Electricity to Elec: / Renovation of Chak No.40/F | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
418 | Provision of Electricity to Reh of Chak No. 175/M, Ramzan Gill | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
419 | Provision of Electricity to Elec: / Renovation Azafi Abadi Chak No.441/6-R Nazar Kamoka | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
420 | Provision of Electricity to Reh: of Basti Ashraf Jutt Wali Chak NO.106/6-R | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
421 | Provision of Electricity to Elec: Renovation Azafi Basti Chak NO.130/6-R | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
422 | Provision of Electricity to Reh of Chak 128/6-R, Master Ghafoor | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
423 | Provision of Electricity to Reh: of Chak No.427/6-R, Allah Ditta Chattah | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
424 | Provision of Electricity to Basti Sultan Jhedu, Rafique Bhatti Chak NO.178/M | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
425 | Reh: of Chak No. 167/M, Haji Maqsood | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
426 | Reh: of Azafi Basti Chak No. 22/3-R, Aslam Mahar | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
427 | Basti Pathan Wali Chak No. 204/M | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
428 | Basti Saleem Khan Pathan Wali 126/M | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
429 | Basti Boota Sial Kotia Chak 44/3-R | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
430 | Reh of Chak No. 34/3-R+Basti Manzor Arrain Wali | HND | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
431 | Reh of Chak No. 13/G, Hafiz M. Akhtar, Ch. Khalid | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
432 | Reh of of Chak 172/M Morr, Basti Chak 124/M Wali | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
433 | Basti Sheikha Wali Chak 206/M | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
434 | Basti Shaban Panwara Wali 141/M | CTN | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
435 | Azafi Basti Chak No. 270/HR Mouza Chak No. 270/HR | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
436 | Azafi Abadi Chak No. 280/HR Mouza Chak No. 280/HR | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
437 | Azafi Basti Chak No. 228/9-R | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
438 | Azafi Basti Chak No. 321/HR Mouza Chak No. 321/HR | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
439 | Azafi Basti Chak No. 320/HR Mouza Chak No. 320/HR | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017
440 | Basti Maqsood Pura Mouza Chak No. 235/9-R | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | Ending 12-2017 | Ending 12-2017

## Phase-II
DEVELOPMENT WORKS REGARDING PRIME MINISTER'S GLOBAL SDGs PROGRAMME IN RESPECT OF DISCOS.
Name of Company: MEPCO |  |  | Phase-II | District Bahawalnagar |  | Status Ending Date: 08-12-2017
Sr. No. | Name of Scheme | Tehsil | District | Financial Progress (Fund utilized) | Physical Progress | Material available | Planned Date of completion Schemes | Actual Date of Completion
1 | Azafi Basti Shamay Khan Panwar 316/HR Tehsil Fortabbas | F/Abbas | B/Nagar | 100% | 100% | All Procured Material Installed | 11-2017 | 11-2017
2 | Basti Pir Bana Wala | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
3 | Basti Haji Allah Ditta Patwari | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
4 | Basti Noor Muhammad Gadhoka | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
5 | Basti Jan Muhammad Arrian | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
6 | Basti Rao Attiq-ur-Rehman | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
7 | Basti Hanif Awan Mouza Mosam Wala | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
8 | Basti Manglan Wali | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
9 | Basti Sarwar Wasand | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
10 | Basti Kharalan Wali | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
11 | Basti Akram Bimbi Ka | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
12 | Basti Khoti Wala Khoo | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
13 | Basti Nazim Shah | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
14 | Bhani Noor Hassan Cheena (Mai Shapa) | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
15 | Azafi Abadi Khair Shah | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
16 | A.A Neza Kodheka Sharqi | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
17 | A.A Neza Kodheka Gharbi | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
18 | Basti Sajwar Khan Dhudhi | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
19 | Basti Mian Ifrahim Beto | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
20 | Basti Iqbal Khkokhar | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
21 | Basti Ashraf Javeed Iqbal Joyia | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
22 | Basti Fazal-ur-Rehman | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
23 | Basti Haji Jan Muhammad | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 01-2018 | 2018-03-01
24 | Basti Lal Khan Kaloka | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
25 | Basti Yaseen Bhatti | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
26 | Basti Mureed Joyia | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
27 | Basti Nasir Dheroka | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
28 | Basti Mian Riaz Dheroka | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
29 | Basti Ahmad Abad | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
30 | Basti Mian Waris Kharal | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
31 | Basti Noor Hassan | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
32 | Azafi Abadi Kaloka Khan Jhoga | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
33 | Basti Mian Sarwar Jamu | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
34 | Basti Sarwar Maken | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
35 | Basti Abdul Ghaffar Joyia | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
36 | Bhani Niaz Ahmad Arrian | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
37 | Bhani Sajid Wali | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
38 | Azafi Abadi Mathela Qaim Ka | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
39 | Basti Yaseen Sial | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
40 | Basti Fareed Nagar | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
41 | Basti Kharalan | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
42 | Azafi Basti Chakki Wali | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
43 | Basti Yaar Muhammad | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
44 | Bhani Bodla Hassan Wala | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
45 | Basi Aman Mughal | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
46 | Basi Dr. Z.A. Syed | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
47 | Basti Mahar Ayoub Near Ranger Check Post | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
48 | Basti Shan Kharal | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
49 | Basti Abdul Sattar Wali | M/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
50 | Reh: Basti Mola Colony Chak No. 58/4R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
51 | Providing Elctricity in Basti Abaid ur Rehman Wali Chak No. 58/4R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
52 | Providing Elctricity in Bati Deen Muhammad Chak No. 55/4R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
53 | Reh: Azafi Basti Chak No. 73/4R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
54 | Reh: Tibba Gharbi Chak No. 48/3R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
55 | Reh: Chak No. 98/6R in Sharqi side Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
56 | Reh: Chak No. 98/6R in Garbi Side Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
57 | Reh: Basti Chak No. 93/6R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 02-2018 | 2018-03-01
58 | Providing Elctricity in Basti Shaikhan wali Chak No. 74/4R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
59 | Providing Elctricity in Sharqi Side Chak No. 84/5R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
60 | Providing Elctricity in Basti Asif Gafoor Chak no. 149/6R Garbi Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
61 | Reh: Chak No. 147/6R towards Madrassa Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
62 | Providing Elctricity in Basti Ahmed Pura Chak No. 76/4R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
63 | Reh: Aafi Basti 121/6R Wala Phatak Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
64 | Providing Elctricity in Chak No. 171/7R Darbar Baba Manzoor Shah Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
65 | Reh: Chak No. 425/6R Basti Ara Wali Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
66 | Chak No. 426/6R Basti Nazeer Jaat Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
67 | Reh: Basti Right Side Chak 133/6R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
68 | Tibba Colony Chak No. 185/7R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
69 | Basti Liaquat Wali Chak 83/5R Tehsil Haroon Abad | H/Abad | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
70 | Basti Pathanon Wali Chak No. 266/HR Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
71 | Azafi Basti Khalid Mehmood 272/HR Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
72 | Reh: Basti Masood Tahir Ward No. 7 Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
73 | Basti Ikhlaq Gharbi Side Ward No. 8 Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
74 | Azafi Basti Tahir Naeem 274/HR Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
75 | Azafi Basti Afzal 231/9R Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
76 | Azafi Basti Abdullah 205/9R Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
77 | Basti Asghar Sial Chak No. 235/9R Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
78 | Basti Tufail Kharel Chak No. 235/9R Tehsil Fort Abbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
79 | Azafi Basti Muhammad Ishaq 205/9R Tehsil Fortabbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
80 | Azafi Basti Furqan Rouf 243/HL Tehsil Fortabbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
81 | Basti Haji Saeed 274/HR Fortabbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01
82 | Azafi Basti Ch. Abdul Munan 212/9R Fortabbas | F/Abbas | B/Nagar | 15% | 10% | Material under procurement | 03-2018 | 2018-03-01